## afss master tracker (
Name | AFSS Management | Property & Building List | DLP Status | Month | AFSS Due Date
au099 South West Industrial Estate | Goodman |  | Not under DLP | JULY | 2026-07-21
Subitems | Fire safety measure | Minimum Standard Performance | Testing Timeframe | Contractor | Testing Date
| 140 days collaboration meeting |  |  | Goodman | 2026-03-09
| Initial collaboration meeting |  |  | Goodman | 2026-03-11
| Quote collaboration meeting |  |  | Goodman
| 30 days collaboration meeting |  |  | Goodman
| All AFSS received |  |  | Goodman
| FFFT |  | 7am Start | Nutech | 2026-04-28
| Owner agent site audit |  |  | SWP | 2026-03-16
| APFS Site Audit |  |  | Flamesafe | 2026-04-28
| Emergency lighting | BCA Part E4.2, E4.4, Spec E1.8, AS 2293.1 – 2005 |  | Tagteam Australia | 2026-04-23
| Exit signs | BCA Part E4.5, E4.6, E4.8, AS 2293.1 – 2005 |  | Tagteam Australia | 2026-04-23
| Fire hydrant system | BCA Part E1.3, AS 2419.1 – 2005 | 15th - 17th April. Flow Test - 15th April | Flamesafe | 2026-04-15
| Fire hose reel systems | BCA Part E1.4, AS 2441 – 2005 | 15th - 17th April. Flow Test - 15th April | Flamesafe | 2026-04-15
| Automatic fire detection and alarm systems | BCA Spec E2.2a, Spec G3.8, AS 1670.1 – 2005 | 15th - 17th April | Flamesafe | 2026-04-15
| Fire doors | AS 1905.1 – 2005, BCA C3.4, C3.11 | 15th - 17th April | Flamesafe | 2026-04-15
| Paths of travel | BCA D1.4, D1.6, D1.7, D1.9, D1.11, D1.12, D2.2, D2.3, D2.8, D2.11, D2.16, D2.17, Clause 186 EP&A Regulation 2000, Visual inspection required & areas to be kept unimpeded and unobstructed at all times. | 15th - 17th April | Flamesafe | 2026-04-15
| Portable fire extinguishers | BCA Part E1.6, Table E1.6, AS 2444 – 2001 | 15th - 17th April | Flamesafe | 2026-04-15
| Smoke & heat vents | BCA Part C2.3, E2.2, Table E2.2b, Spec E2.2c, NSW H101.22, AS 2665 – 2001 | 7am Start | Nutech | 2026-04-28
| Automatic fire suppression system | BCA Part E1.5 and spec E1.5, AS 2118.1 – 1999 & CA-16 (Main Warehouse) | 15th - 17th April. Flow Test - 15th April | Flamesafe | 2026-04-15
| Smoke detectors and heat detectors | Part E2 of BCA, AS 1670.1 – 2004, (Main office) | 15th - 17th April | Flamesafe | 2026-04-15
| Fire safety & emergency evacuation procedure | AS 3745 – 2002 | 8am Start | Adair | 2026-05-11
| Perimeter vehicle access for emergency vehicles | BCA Part C2.3 and C2.4 | 15th - 17th April | Flamesafe | 2026-04-28 09:00
| Fire alarm monitoring (Alarm signalling equipment) | AS 1670.3 monitoring network performance (primary link – radio pocket transmission medium AS 3013 – wiring ASE to network connection point to second link AS 4228.6 – Alarm signalling equipment ASE Maintained to original installation |  | JCI ( ADT)