## REPAIRS
Flamesafe Fire — Repairs Register · 08 April 2026
123 active repairs · Total value: $458,419 · Authorised: $447,319 · Unassigned: $156,756 · Sorted: highest priority first · Use filters + dropdowns to organise
AUTHORISED — SCHEDULE NOW |  |  | UNASSIGNED — DISPATCH NOW |  |  | CRITICAL PRIORITY |  |  | HIGH PRIORITY
447319.1139 |  |  | 156756.0839 |  |  | 10 |  |  | 70
PRIORITY | REF | PROPERTY / SITE | CLIENT | DAYS OPEN | STATUS | TECHNICIAN | VALUE ($) | AUTH ($) | SCHED DATE | INVOICED | NOTES / ACTION
CRITICAL | T-33490 | Costas - 4 Beach Street, Eastern Creek, NSW 2766 | Lendlease Real Estate Investme | 36 | REVISIT | Gordon Jenkins | 29772.4184 | 29772.42 | 2026-04-15 06:00 | No
CRITICAL | T-19009 | MONDC - 13 Bushmaster Avenue, Moorebank, NSW 2170 | Primary Connect | 188 | REVISIT | Gordon Jenkins | 14387.3845 | 14387.38 | 2025-10-28 07:35 | No
CRITICAL | T-20036 | Foothills Distribution Centre - 30 Lidco Street, A | The Trustee For Gemstone Arnde | 174 | REVISIT | Gordon Jenkins | 13244.1535 | 13244.15 | 2025-11-05 07:00 | No
CRITICAL | T-09869 | Impact International - Cnr Victoria and O’Connell | Impact International | 372 | REVISIT | Bailey Arthur | 12263.736 | 12263.74 | 2025-04-29 11:55 | No
CRITICAL | T-12542 | Pittking Properties - 175-181 Oxford Street, Bondi | C/- Steven Krulis Real Estate | 305 | REVISIT | John Minai | 11120.0209 | 11120.02 | 2026-03-03 09:05 | No
CRITICAL | T-14463 | Kraft Heinz - 92-96 Station Road, Seven Hills, NSW | Kraft-Heinz Co Australia Ltd | 250 | REVISIT | Gordon Jenkins | 10484 | 10484 | 2025-08-01 09:00 | No
CRITICAL | T-12370 | Frutex - 20 St Albans Road, Kingsgrove, NSW 2208 | Sterilisation Technologies Aus | 312 | REVISIT | Gordon Jenkins | 10090.053 | 10090.05 | 2026-01-07 08:17 | No
CRITICAL | T-26046 | 28 Percival Road, Smithfield, NSW 2164 | Lendlease Real Estate Investme | 112 | REVISIT | Nu Unasa | 10056.493 | 10056.49 | 2026-01-05 08:00 | No
CRITICAL | T-33630 | Baxter - 164 Newton Road, Wetherill Park, NSW 2164 | Centuria Property Funds No. 2 | 34 | REVISIT | Gordon Jenkins | 13702.25 | 13702.25 | 2026-03-04 12:00 | No
CRITICAL | T-30892 | 144 Hartley Road, Smeaton Grange, NSW 2567 | Centuria Institutional Investm | 61 | READY |  | 13457.86 | 13457.86 |  | No
HIGH | T-17558 | Pengton - 80 George Street, Parramatta, NSW 2150 | Pengton No. 1 Pty Ltd ATF Peng | 207 | REVISIT | Gordon Jenkins | 7507.5684 | 7507.57 | 2025-09-16 09:00 | No
HIGH | T-23333 | Foothills Distribution Centre - 30 Lidco Street, A | The Trustee For Gemstone Arnde | 137 | REVISIT | Nu Unasa | 7430 | 7430 | 2026-02-05 07:10 | No
HIGH | T-20080 | Elizabeth Towers - 418A Elizabeth Street, Surry H | X Commercial | 173 | REVISIT | Nu Unasa | 7065.508 | 7065.52 | 2025-11-06 07:00 | No
HIGH | T-26002 | ACU - Building 600-650 - 25a Baker Road, Strathfie | Australian Catholic Universiti | 113 | REVISIT | Nu Unasa | 5834.7131 | 5834.72 | 2026-01-29 06:00 | Yes
HIGH | T-25482 | Jaycar Electronics Group - 46 Eastern Creek Drive, | Electus Distribution Pty Ltd | 118 | REVISIT | John Minai | 5383.0095 | 5383.01 | 2026-02-03 06:00 | No
HIGH | T-16225 | Labour Council of NSW - 377-383 Sussex Street, Syd | Unions NSW Property and Servic | 223 | REVISIT | John Minai | 5090 | 5090 | 2025-12-18 10:00 | No
HIGH | T-19012 | Ontex - 5 Wonderland Drive, Eastern Creek, NSW 276 | One Funds Management Limited A | 188 | REVISIT | Nu Unasa | 4728.67 | 4728.66 | 2025-10-08 07:00 | No
HIGH | T-14358 | Visy Recycling - 112 Euston Road, Alexandria, NSW | Jones Lang LaSalle (NSW) Pty L | 252 | REVISIT | Nu Unasa | 4500 | 4500 |  | No
HIGH | T-23677 | Frutex - 20 St Albans Road, Kingsgrove, NSW 2208 | Sterilisation Technologies Aus | 132 | REVISIT | Gordon Jenkins | 4038.228 | 4038.23 | 2026-01-07 06:00 | No
HIGH | T-22186 | Union NSW - 4-10 Goulburn Street, Sydney, NSW 2000 | C/- Colliers Int’l Pty Ltd | 148 | REVISIT | Gordon Jenkins | 3270 | 3270 | 2025-12-18 11:00 | No
HIGH | T-19273 | Metrolink Corporate Park - 197-201 Coward Street | The Trust Company (Australia) | 181 | REVISIT | Nu Unasa | 2895.008 | 2895.01 | 2025-10-16 07:00 | No
HIGH | T-25283 | Resolution X - 21B Richmond Road, Homebush West, N | Cranden Investments Pty Ltd | 120 | REVISIT | Nu Unasa | 2640 | 2640 | 2026-03-20 09:00 | No
HIGH | T-13540 | 223-225 Liverpool Street, Darlinghurst, NSW 2010 | Forza Capital Pty Ltd ATF Forz | 279 | REVISIT | Gordon Jenkins | 2628.002 | 2628 | 2025-11-27 07:30 | No
HIGH | T-17260 | Fred Health & Bleach - 24 Rothschild, Rosebery, NS | C/- TGC | 211 | REVISIT | Ryan Robinson | 2528.0025 | 2528 | 2025-09-19 11:00 | No
HIGH | T-05579 | 1 Wentworth Street, Parramatta, NSW 2150 | N G P Investments (no 2) Pty L | 454 | REVISIT | Darren Brailey | 2351.01 | 2351.01 | 2025-01-10 12:32 | No
HIGH | T-13630 | 49 Hotham Parade, Artarmon, NSW 2064 | Jones Lang LaSalle (NSW) Pty L | 274 | REVISIT | John Minai | 2110.0006 | 2110 | 2025-08-08 13:10 | No
HIGH | T-16132 | Australasia Chambers - 2 Martin Place, Sydney, NSW | Paspaley Pearls Properties Pty | 225 | REVISIT | Nu Unasa | 2080 | 2080 | 2025-09-09 09:00 | No
HIGH | T-23206 | 28 Britton Street, Smithfield | CBIIP 28B Pty Ltd | 138 | REVISIT | Gordon Jenkins | 2098.7851 | 2098.78 | 2025-11-21 11:06 | No
HIGH | T-21019 | Goodman Fielder - 16 Templar Rd, Erskine Park, NSW | Goodman Fielder Consumer Foods | 158 | REVISIT | Gordon Jenkins | 1893.003 | 1893 |  | No
HIGH | T-19016 | Westlands Industrial Estate - 33-45 James Erskine | Knight Frank | 188 | REVISIT | Gordon Jenkins | 1560.006 | 1560.01 | 2025-10-02 12:39 | No
HIGH | T-22476 | Pacific Square - 717 Anzac Parade, Maroubra, NSW 2 | Excel Building Management | 145 | REVISIT | Nu Unasa | 1630.63 | 1630.63 | 2025-11-28 10:00 | No
HIGH | T-23039 | 77 Scott Avenue, Leura, NSW 2780 | Yao Kai Pty Ltd | 139 | REVISIT | Gordon Jenkins | 1195.282 | 1195.28 | 2025-11-26 11:00 | No
HIGH | T-12719 | 20-22 Mons Road, Westmead, NSW 2145 | Barwon Investment Partners Pty | 295 | REVISIT | Gordon Jenkins | 1067.006 | 1067.01 | 2025-09-23 07:00 | No
HIGH | T-25088 | Goodman AU210 - Gateway Industrial Estate - Buildi | Goodman Property Services (Aus | 124 | REVISIT | Nu Unasa | 1040.001 | 1040 | 2026-01-30 06:00 | No
HIGH | T-26206 | Goodman AU877 - Silverwater D/C - Light & Wonder - | Goodman Property Services (Aus | 111 | REVISIT | Gordon Jenkins | 1040.004 | 1040 | 2026-01-30 08:10 | No
HIGH | T-12700 | Goodman AU099 - 31 Heathcote Road, Moorebank, NSW, | Goodman Property Services (Aus | 298 | REVISIT | Gordon Jenkins | 1040.004 | 1040 | 2026-02-05 12:00 | No
HIGH | T-22478 | SP 74790 - The Panorama - 717 Anzac Parade Maroub | Excel Building Management | 145 | REVISIT | Nu Unasa | 843.5 | 843.5 | 2025-11-28 13:00 | No
HIGH | T-13526 | SP 722 - 167 Victoria Road, Bellevue Hill, NSW 202 | Strata Plan 722 | 280 | REVISIT | Nu Unasa | 800.003 | 800 | 2025-07-16 07:15 | No
HIGH | T-25090 | Mercedes Benz - 43-47 O’Riordan Street, Alexandria | LSH Auto (Sydney) Pty Ltd | 124 | REVISIT | Nu Unasa | 734.001 | 734 | 2025-12-16 09:00 | No
HIGH | T-27443 | ARBOUR - 63-65 Burrows Road, Alexandria, NSW 2015 | Arbor Property | 92 | REVISIT | Nu Unasa | 292 | 292 | 2026-01-19 14:00 | No
HIGH | T-24611 | De Luxe - 7 Blackfriars Street, Chippendale, NSW 2 | DS Holdings and de Luxe Nomine | 127 | REVISIT | John Minai | 342.0024 | 342 | 2025-12-09 09:00 | No
HIGH | T-19704 | The Kitchenary - 27 Holbeche Road, Arndell Park, N | The Kitchenary Pty Ltd | 176 | READY | Gordon Jenkins | 4030.39 | 4030.39 |  | No
HIGH | T-19670 | Linfox Workshop Service Centre - 65 Lenore Drive, | Linfox Australia | 179 | READY |  | 3278 | 3278 |  | No
HIGH | T-19049 | Compass Centre - 85 North Terrace Bankstown, NSW 2 | Knight Frank | 187 | READY |  | 3104 | 3104 |  | No
HIGH | T-15516 | 88 Phillip Street, Parramatta, NSW 2150 | AM Property Plus C/- IOOF Inve | 238 | READY | Gordon Jenkins | 2780.003 | 2780 | 2025-08-21 08:00 | No
HIGH | T-15015 | 11 Hexham Place, Wetherill Park, NSW 2164 | CSOF Sub Trust No. 2 ABN 52 84 | 249 | READY | Gordon Jenkins | 2360 | 2360 |  | No
HIGH | T-10160 | Northcote Pottery Australia - 2 Distribution Place | Grand Hill Pty Ltd | 361 | READY |  | 1970 | 1970 |  | No
HIGH | T-14357 | Zirco Data - 1 Johnson Road, Campbelltown, NSW 25 | Lendlease Funds Management Ltd | 252 | READY |  | 6400 |  |  | No
HIGH | T-13935 | Australasia Chambers - 2 Martin Place, Sydney, NSW | Paspaley Pearls Properties Pty | 264 | REVISIT | John Minai | 1200 |  | 2025-07-21 07:00 | No
HIGH | T-31022 | YORKAY - 131 York Street, Sydney, NSW 2000 | C/- MMJ Sydney Pty Ltd | 60 | REVISIT | Nu Unasa | 4947.5221 | 4947.53 | 2026-03-03 06:00 | No
HIGH | T-29184 | Sebel - 48 Airds Road, Minto, NSW 2566 | KNAPP & Associates | 76 | REVISIT | Gordon Jenkins | 4630.008 | 4630.01 | 2026-01-27 09:56 | No
HIGH | T-31757 | D.J.Wear - 117 York Street, Sydney, NSW 2000 | 117 York Street Pty Limited | 50 | REVISIT | Nu Unasa | 4568.813 | 4568.8 | 2026-02-25 08:30 | No
HIGH | T-30824 | Goodman AU002 - Slough Business Park - 2 Slough Av | Goodman Property Services (Aus | 62 | REVISIT | John Minai | 3435.009 | 3435.01 | 2026-02-24 10:45 | No
HIGH | T-33542 | Building B1, B2, B3 - 5 Williamson Rd, Ingleburn N | Ingleburn Industrial Property | 35 | REVISIT | Gordon Jenkins | 3183.004 | 3183 | 2026-03-06 10:00 | No
HIGH | T-31417 | Cotton King - 95 Bonds Road, Punchbowl, NSW 2196 | Uturn Reuse Pty Limited | 55 | REVISIT | Gordon Jenkins | 3133.2258 | 3133.22 | 2026-02-23 06:00 | No
HIGH | T-28546 | ACU - Building 502 - 40 Edward Street, North Sydne | Australian Catholic Universiti | 83 | REVISIT | Gordon Jenkins | 2431.2052 | 2431.2 | 2026-02-02 06:00 | No
HIGH | T-31091 | Linfox - 3 Harris Avenue, Marsden Park, NSW 2765 | Linfox Australia | 57 | REVISIT | Gordon Jenkins | 2340 | 2340 | 2026-02-27 06:00 | No
HIGH | T-32774 | Toll - 11A Greenhills Avenue, Moorebank, NSW 2170 | Vassk Investments Pty Ltd ATF | 39 | REVISIT | Nick Hollingsworth | 2388.008 | 2388 | 2026-03-05 11:36 | No
HIGH | T-34390 | Goodman AU240 - Park View Business Park - 3 Talave | Goodman Property Services (Aus | 28 | REVISIT | Gordon Jenkins | 7392.3055 | 7392.3 | 2026-03-26 07:01 | No
HIGH | T-31974 | Club Ashfield - 1-11 Charlotte Street, Ashfield, N | Ashfield Catholic & Community | 48 | REVISIT | John Minai | 2425.8222 | 2425.82 | 2026-03-18 06:00 | No
HIGH | T-31153 | Linfox - 3 Harris Avenue, Marsden Park, NSW 2765 | Linfox Australia | 57 | REVISIT | John Minai | 2050.005 | 2050 | 2026-02-17 06:00 | No
HIGH | T-29386 | 30 Loftus Road, Yennora , NSW 2161 | West Infill Sub TC PTY LTD ATF | 74 | REVISIT | Gordon Jenkins | 2069.927 | 2069.93 | 2026-02-05 09:28 | No
HIGH | T-28547 | ACU - Building 520 - 3 Berry Street, North Sydney, | Australian Catholic Universiti | 83 | REVISIT | Nu Unasa | 1560.006 | 1560.01 | 2026-02-02 10:00 | No
HIGH | T-29685 | N&A & ACR - 10-12 Distribution Drive, Orchard Hill | TCAL ATF Altis Bulky Sub Trust | 69 | REVISIT | Gordon Jenkins | 1315.8271 | 1315.83 | 2026-02-03 13:21 | No
HIGH | T-32615 | PFM Corp (BLDG 2) - 147-151 Newton Road, Wetherill | Kenneth R Moras Property Holdi | 41 | REVISIT | John Minai | 1040.004 | 1040 | 2026-03-12 06:00 | No
HIGH | T-33494 | Space 207 - 207 Pacific Highway, St Leonards, NSW | Altis Bulky Retail ATF Altis B | 36 | REVISIT | John Minai | 1040 | 1040 | 2026-03-09 06:00 | No
HIGH | T-32351 | Goodman AU002 - Slough Business Park - Block A Uni | Goodman Property Services (Aus | 43 | REVISIT | John Minai | 650 | 650 | 2026-02-24 11:00 | No
HIGH | T-33860 | City of Parramatta Council - 9 Wentworth Street, P | C/- Colliers Int’l Pty Ltd | 33 | REVISIT | Nu Unasa | 520.002 | 520 | 2026-04-10 11:00 | No
HIGH | T-36512 | COLES RRM - 54 Templar Road, Erskine Park, NSW 275 | Retail Ready Operations Austra | 12 | READY |  | 9692 | 9692 |  | No
HIGH | T-26567 | 28 Rodborough Road, Frenchs Forest, NSW 2086 | C/- TGC | 106 | SCHEDULED |  | 7976.342 | 7976.34 | 2026-01-09 06:00 | No
HIGH | T-21783 | TRS - 170 Newton Road, Wetherill Park, NSW 2164 | Newton Road Holdings Pty Ltd | 154 | SCHEDULED | Gordon Jenkins | 7796 | 7796 | 2026-09-25 06:00 | No
HIGH | T-11638 | Bronson & Jacobs - 70 Marple Avenue, Villawood, NS | George Vasili & Nick Vasili C/ | 326 | SCHEDULED |  | 7105.15 | 7105.15 | 2026-03-16 06:00 | No
HIGH | T-38842 | 15-19 McPherson St, Banksmeadow, NSW 2019 | Roth Industrial | -1 | REVISIT | Gordon Jenkins | 1660 | 1660 | 2026-04-09 07:00 | No
HIGH | T-36078 | Silverwater Industrial Park - Corner Fariola St, | Lendlease Real Estate Investme | 14 | REVISIT | Gordon Jenkins | 1040.004 | 1040 | 2026-04-14 06:00 | No
HIGH | T-11659 | CEVA - 9-11 Distribution Drive, Orchard Hills, NSW | TCAL ATF Altis Bulky Sub Trust | 322 | SCHEDULED |  | 5980 | 5980 | 2025-06-25 06:45 | No
HIGH | T-24771 | Goodman AU058 - Bungaribee Industrial Estate - 71 | Goodman Property Services (Aus | 125 | SCHEDULED |  | 5786.554 | 5786.55 | 2025-12-10 10:00 | No
HIGH | T-28579 | 7 Box Road, Taren Point, NSW 2229 | 7 Box Sub TC Pty Ltd ATF 7 Box | 82 | READY |  | 650.0025 | 650 |  | No
HIGH | T-36205 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ - | 13 | REVISIT | Gordon Jenkins | 590 | 590 | 2026-03-25 11:30 | No
HIGH | T-36204 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ - | 13 | REVISIT | Gordon Jenkins | 520 | 520 | 2026-03-25 07:30 | No
HIGH | T-39040 | Goodman AU019 - Transtech Business Park - 12 Mars | Goodman Property Services (Aus | -1 | READY |  | 4972 | 4972 |  | No
MEDIUM | T-38941 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ - | -1 | READY |  | 4575.2 | 4575.2 |  | No
MEDIUM | T-09968 | 1A The Crescent, Kingsgrove, NSW 2208 | Vanessa Aus Sub TC Pty Ltd ATF | 364 | SCHEDULED | Nu Unasa | 4195.004 | 4195 | 2025-09-19 09:00 | No
MEDIUM | T-36070 | Goodman AU059 - Lidcombe Business Park - Building | Goodman Property Services (Aus | 14 | READY |  | 3900 | 3900 |  | No
MEDIUM | T-35278 | 609-615 Harris Street, Ultimo, NSW 2007 | Clara & Matthew Pty Ltd | 21 | READY |  | 3700.006 | 3700.01 |  | No
MEDIUM | T-38380 | Australasia Chambers - 2 Martin Place, Sydney, NSW | Paspaley Pearls Properties Pty | 5 | READY |  | 3585.008 | 3585.01 |  | No
MEDIUM | T-26708 | Goodman AU546 - Interlink Industrial Estate - 28 S | Goodman Property Services (Aus | 99 | SCHEDULED | Gordon Jenkins | 3555.9162 | 3555.91 | 2026-01-21 10:00 | No
MEDIUM | T-03094 | LOGOS - Sigma Healthcare - 2 Imperata Close, Kemps | Logos Property Management Pty | 495 | SCHEDULED |  | 3000 | 3000 | 2025-06-27 07:00 | No
MEDIUM | T-22247 | SP 722 - 167 Victoria Road, Bellevue Hill, NSW 202 | Strata Plan 722 | 147 | SCHEDULED | Darren Brailey | 2554.432 | 2554.43 | 2025-11-27 12:00 | No
MEDIUM | T-39042 | Goodman AU877 - Silverwater D/C - Light & Wonder - | Goodman Property Services (Aus | -1 | READY |  | 2390 | 2390 |  | No
MEDIUM | T-38611 | White Horse - 381 Crown St, Surry Hills | PDC Tech Pty Ltd | 0 | READY |  | 2380.003 | 2380 |  | Yes
MEDIUM | T-23236 | Storhub - 128 Milperra Road, Revesby, NSW 2212 | StorHub Australia | 138 | SCHEDULED |  | 2335.608 | 2335.61 | 2025-12-08 06:00 | No
MEDIUM | T-17666 | Costas - 4 Beach Street, Eastern Creek, NSW 2766 | Jones Lang LaSalle (NSW) Pty L | 204 | SCHEDULED |  | 2267.884 | 2267.88 | 2025-09-25 07:00 | No
MEDIUM | T-33543 | ACU - Building 533 - 33 Berry Street, North Sydney | Knight Frank | 35 | INPROGRESS | Nu Unasa | 1740 | 1160 | 2026-03-21 08:00 | No
MEDIUM | T-14097 | AUSTCOR - 159-163 Newton Road Wetherell Park, NSW | Aliro Trusco 1 Pty Ltd ATF the | 257 | SCHEDULED | Gordon Jenkins | 1630 | 1630 | 2025-11-24 09:00 | No
MEDIUM | T-17897 | Andrews Meats - 38 Birnie Avenue, Lidcombe, NSW 21 | Andrews Meat Industries Pty Lt | 200 | SCHEDULED |  | 1560 | 1560 | 2025-10-14 14:00 | No
MEDIUM | T-36567 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ - | 12 | READY |  | 1027 | 1027 |  | No
MEDIUM | T-36568 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ - | 12 | READY |  | 1027 | 1027 |  | No
MEDIUM | T-22477 | SP 74405 - The Northerly - 717 Anzac Parade Marou | Excel Building Management | 145 | SCHEDULED | Gordon Jenkins | 843.5 | 843.5 | 2025-11-28 12:00 | No
MEDIUM | T-32310 | NKS - 2 Eden Park Drive, Macquarie Park, NSW 2113 | Nks (NSW) Pty Ltd C/- Dunnet P | 43 | INPROGRESS | Hugo | 680.63 | 1161.26 | 2026-02-23 12:00 | No
MEDIUM | T-12518 | 2A / 2B Culverston Road, Minto, NSW, 2566 | The Trust Company Limited in i | 307 | SCHEDULED | Nu Unasa | 590 | 590 | 2025-09-15 09:00 | No
MEDIUM | T-38790 | LOGOS - Sigma Healthcare - 2 Imperata Close, Kemps | Logos Property Management Pty | 0 | READY |  | 520.002 | 520 |  | No
MEDIUM | T-14356 | 36 Honeycomb Drive, Eastern Creek, NSW 2766 | Jones Lang LaSalle (NSW) Pty L | 252 | SCHEDULED |  | 3500 |  | 2025-10-14 11:00 | No
MEDIUM | T-36635 | COLES RRM - 54 Templar Road, Erskine Park, NSW 275 | Retail Ready Operations Austra | 11 | SCHEDULED |  | 9587.818 | 9587.82 | 2026-05-05 06:00 | No
MEDIUM | T-28601 | Ya Zhou Wen Hua Enterprises - 541-543 Kent Street, | C/- ED Realty | 82 | SCHEDULED |  | 4174.009 | 4174.01 | 2026-02-06 06:00 | No
MEDIUM | T-28480 | State Library of NSW - 1 Shakespeare Place, Sydney | State Library of NSW | 83 | SCHEDULED |  | 3906.208 | 3906.21 | 2026-01-16 06:00 | No
MEDIUM | T-32509 | 26 Nelson Road, Yennora, NSW 2161 | The Trust Company (Australia) | 42 | SCHEDULED |  | 3283.2348 | 3283.24 | 2026-04-23 06:00 | No
MEDIUM | T-33531 | Mandarin Centre - 65 Albert Ave, Chatswood NSW 206 | Mandarin Developments Pty Ltd | 35 | SCHEDULED |  | 2865.004 | 2865 | 2026-04-14 06:00 | No
MEDIUM | T-31681 | KB House - 72-76 Archer Street, Chatswood, NSW 206 | Shead Real Estate Pty Ltd | 53 | SCHEDULED |  | 1985 | 1985 | 2026-02-18 06:00 | No
MEDIUM | T-32610 | Goodman AU820 - City West Office Park - Building A | Goodman Property Services (Aus | 41 | SCHEDULED |  | 1670.762 | 1670.76 | 2026-04-27 06:00 | No
MEDIUM | T-32692 | Precinct 5 AU186 - 3 Tundra Close, Kemps Kreek, NS | Goodman Property Services (Aus | 40 | SCHEDULED |  | 660.513 | 660.51 | 2026-03-11 12:00 | No
MEDIUM | T-36072 | Space 207 - 207 Pacific Highway, St Leonards, NSW | Altis Bulky Retail ATF Altis B | 14 | SCHEDULED |  | 5673.04 | 5673.04 | 2026-04-29 06:00 | No
MEDIUM | T-38942 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ - | -1 | SCHEDULED |  | 5238.4 | 5238.4 |  | No
MEDIUM | T-36829 | Gateway Business Park - Unit 3/9/10 - 63-79 Parram | Cambooya Properties C/o Knight | 11 | SCHEDULED |  | 3190 | 3190 | 2026-04-08 07:00 | No
MEDIUM | T-34915 | 11-13 Orion Road, Lane Cove West, NSW 2066 | The Trustee for Gemstone Lane | 25 | SCHEDULED |  | 1753.9506 | 1753.96 | 2026-04-28 06:00 | No
MEDIUM | T-36467 | Goodman AU059 Lidcombe Business Park (Buildings A | Goodman Property Services (Aus | 12 | SCHEDULED |  | 1733.413 | 1733.41 | 2026-05-01 06:00 | No
MEDIUM | T-37159 | Jacfin Ricoh - 4 Telopea Place, Eastern Creek, NS | FlameSafe Warranty (Contracts) | 8 | SCHEDULED |  | 1325.0025 | 1325 | 2026-04-13 06:00 | No
MEDIUM | T-34395 | PPIF - 9 George Street, Parramatta, NSW 2150 | Talish Property Group C/- Knig | 28 | SCHEDULED |  | 780.003 | 780 | 2026-03-25 08:00 | No
MEDIUM | T-35708 | NIMBE - 39-47 Regent Street, Chippendale, NSW 2008 | Intera Group | 19 | SCHEDULED |  | 700.102 | 700.1 | 2026-03-26 10:00 | No
MEDIUM | T-36631 | Freight Assist Australia - 26 Pavesi Street, Guild | Cambooya Properties C/- Knight | 11 | SCHEDULED |  | 650.0025 | 650 | 2026-05-04 06:00 | No
MEDIUM | T-36074 | Labour Council of NSW - 377-383 Sussex Street, Syd | Unions NSW Property and Servic | 14 | SCHEDULED |  | 460 | 460 | 2026-04-30 06:00 | No
MEDIUM | T-35710 | ACU - Building 526 - 8-10 Berry Street, North Sydn | Australian Catholic Universiti | 19 | SCHEDULED |  | 520.002 | 520 | 2026-03-27 09:00 | No
MEDIUM | T-38182 | Kraft Heinz - 92-96 Station Road, Seven Hills, NSW | Kraft-Heinz Co Australia Ltd | 5 | SCHEDULED |  | 460 | 460 | 2026-04-07 12:00 | No
MEDIUM | T-39238 | Goodman AU106 - M5 Industry Park - Building 1 - 1 | Goodman Property Services (Aus | -2 | SCHEDULED |  | 0 | 1818.5 | 2026-04-10 12:00 | No
123 of 123 repairs shown | [6 empty] | 458419.1139 | 449038.16

## NOTES LOG
Flamesafe Fire — Task Notes & Status Change Log
Paste updates in chat → held until requested · Written here on demand · Every entry timestamped, nothing overwritten
DATE / TIME | TASK REF | PROPERTY / CLIENT | STATUS — BEFORE | STATUS — AFTER | NOTE | FOLLOW-UP DATE | LOGGED BY
09/04/2026 | T-19012 | Ontex — 5 Wonderland Drive, Eastern Creek | REVISIT | REVISIT | NEEDS REQUOTE — 2 men 8hrs, I/O module, 100m cable, boom lift, 2 horns to relocate. Batteries replaced as per report. |  | Casper Tavitian
09/04/2026 | T-33494 | Space 207 — 207 Pacific Highway, St Leonards | REVISIT | REVISIT | FIP critical defects — T-Gen 50 slave amplifier faulty levels 4 to roof. Needs 2 techs. Full impedance investigation required. |  | Casper Tavitian
↑ Example entries (greyed) · Live log entries begin below ↓

## ACTION LIST
Flamesafe Fire — Action List · All Active Tasks · 08 April 2026
179 active tasks · $512,648 total value · Sorted by priority score · Use column filters to focus
# | PRIORITY | REF | PROPERTY / SITE | CLIENT | STATUS | TECHNICIAN | CATEGORY | VALUE ($) | AUTH ($) | DAYS OPEN | SCHED DATE | INVOICED
1 | CRITICAL | T-33490 | Costas - 4 Beach Street, Eastern Creek, NSW 2766 | Lendlease Real Estate Invest | REVISIT | Gordon Jenkins | Repair | 29772.4184 | 29772.42 | 36 | 2026-04-15 06:00 | No
2 | CRITICAL | T-19009 | MONDC - 13 Bushmaster Avenue, Moorebank, NSW 2170 | Primary Connect | REVISIT | Gordon Jenkins | Repair | 14387.3845 | 14387.38 | 188 | 2025-10-28 07:35 | No
3 | CRITICAL | T-20036 | Foothills Distribution Centre - 30 Lidco Street, A | The Trustee For Gemstone Arn | REVISIT | Gordon Jenkins | Repair | 13244.1535 | 13244.15 | 174 | 2025-11-05 07:00 | No
4 | CRITICAL | T-09869 | Impact International - Cnr Victoria and O’Connell | Impact International | REVISIT | Bailey Arthur | Repair | 12263.736 | 12263.74 | 372 | 2025-04-29 11:55 | No
5 | CRITICAL | T-12542 | Pittking Properties - 175-181 Oxford Street, Bondi | C/- Steven Krulis Real Estat | REVISIT | John Minai | Repair | 11120.0209 | 11120.02 | 305 | 2026-03-03 09:05 | No
6 | CRITICAL | T-14463 | Kraft Heinz - 92-96 Station Road, Seven Hills, NSW | Kraft-Heinz Co Australia Ltd | REVISIT | Gordon Jenkins | Repair | 10484 | 10484 | 250 | 2025-08-01 09:00 | No
7 | CRITICAL | T-12370 | Frutex - 20 St Albans Road, Kingsgrove, NSW 2208 | Sterilisation Technologies A | REVISIT | Gordon Jenkins | Repair | 10090.053 | 10090.05 | 312 | 2026-01-07 08:17 | No
8 | CRITICAL | T-26046 | 28 Percival Road, Smithfield, NSW 2164 | Lendlease Real Estate Invest | REVISIT | Nu Unasa | Repair | 10056.493 | 10056.49 | 112 | 2026-01-05 08:00 | No
9 | CRITICAL | T-33630 | Baxter - 164 Newton Road, Wetherill Park, NSW 2164 | Centuria Property Funds No. | REVISIT | Gordon Jenkins | Repair | 13702.25 | 13702.25 | 34 | 2026-03-04 12:00 | No
10 | CRITICAL | T-30892 | 144 Hartley Road, Smeaton Grange, NSW 2567 | Centuria Institutional Inves | READY |  | Repair | 13457.86 | 13457.86 | 61 |  | No
11 | CRITICAL | T-00911 | 203-209 Northumberland Street, Liverpool - NSW 206 | Inner West Council C/- Knigh | SCHEDULED | Nu Unasa | Callout | 15682 |  | 551 | 2025-01-24 12:00 | No
12 | HIGH | T-17558 | Pengton - 80 George Street, Parramatta, NSW 2150 | Pengton No. 1 Pty Ltd ATF Pe | REVISIT | Gordon Jenkins | Repair | 7507.5684 | 7507.57 | 207 | 2025-09-16 09:00 | No
13 | HIGH | T-23333 | Foothills Distribution Centre - 30 Lidco Street, A | The Trustee For Gemstone Arn | REVISIT | Nu Unasa | Repair | 7430 | 7430 | 137 | 2026-02-05 07:10 | No
14 | HIGH | T-20080 | Elizabeth Towers - 418A Elizabeth Street, Surry H | X Commercial | REVISIT | Nu Unasa | Repair | 7065.508 | 7065.52 | 173 | 2025-11-06 07:00 | No
15 | HIGH | T-26002 | ACU - Building 600-650 - 25a Baker Road, Strathfie | Australian Catholic Universi | REVISIT | Nu Unasa | Repair | 5834.7131 | 5834.72 | 113 | 2026-01-29 06:00 | Yes
16 | HIGH | T-25482 | Jaycar Electronics Group - 46 Eastern Creek Drive, | Electus Distribution Pty Ltd | REVISIT | John Minai | Repair | 5383.0095 | 5383.01 | 118 | 2026-02-03 06:00 | No
17 | HIGH | T-16225 | Labour Council of NSW - 377-383 Sussex Street, Syd | Unions NSW Property and Serv | REVISIT | John Minai | Repair | 5090 | 5090 | 223 | 2025-12-18 10:00 | No
18 | HIGH | T-19012 | Ontex - 5 Wonderland Drive, Eastern Creek, NSW 276 | One Funds Management Limited | REVISIT | Nu Unasa | Repair | 4728.67 | 4728.66 | 188 | 2025-10-08 07:00 | No
19 | HIGH | T-14358 | Visy Recycling - 112 Euston Road, Alexandria, NSW | Jones Lang LaSalle (NSW) Pty | REVISIT | Nu Unasa | Repair | 4500 | 4500 | 252 |  | No
20 | HIGH | T-23677 | Frutex - 20 St Albans Road, Kingsgrove, NSW 2208 | Sterilisation Technologies A | REVISIT | Gordon Jenkins | Repair | 4038.228 | 4038.23 | 132 | 2026-01-07 06:00 | No
21 | HIGH | T-22186 | Union NSW - 4-10 Goulburn Street, Sydney, NSW 2000 | C/- Colliers Int’l Pty Ltd | REVISIT | Gordon Jenkins | Repair | 3270 | 3270 | 148 | 2025-12-18 11:00 | No
22 | HIGH | T-19273 | Metrolink Corporate Park - 197-201 Coward Street | The Trust Company (Australia | REVISIT | Nu Unasa | Repair | 2895.008 | 2895.01 | 181 | 2025-10-16 07:00 | No
23 | HIGH | T-25283 | Resolution X - 21B Richmond Road, Homebush West, N | Cranden Investments Pty Ltd | REVISIT | Nu Unasa | Repair | 2640 | 2640 | 120 | 2026-03-20 09:00 | No
24 | HIGH | T-13540 | 223-225 Liverpool Street, Darlinghurst, NSW 2010 | Forza Capital Pty Ltd ATF Fo | REVISIT | Gordon Jenkins | Repair | 2628.002 | 2628 | 279 | 2025-11-27 07:30 | No
25 | HIGH | T-17260 | Fred Health & Bleach - 24 Rothschild, Rosebery, NS | C/- TGC | REVISIT | Ryan Robinson | Repair | 2528.0025 | 2528 | 211 | 2025-09-19 11:00 | No
26 | HIGH | T-05579 | 1 Wentworth Street, Parramatta, NSW 2150 | N G P Investments (no 2) Pty | REVISIT | Darren Brailey | Repair | 2351.01 | 2351.01 | 454 | 2025-01-10 12:32 | No
27 | HIGH | T-16132 | Australasia Chambers - 2 Martin Place, Sydney, NSW | Paspaley Pearls Properties P | REVISIT | Nu Unasa | Repair | 2080 | 2080 | 225 | 2025-09-09 09:00 | No
28 | HIGH | T-13630 | 49 Hotham Parade, Artarmon, NSW 2064 | Jones Lang LaSalle (NSW) Pty | REVISIT | John Minai | Repair | 2110.0006 | 2110 | 274 | 2025-08-08 13:10 | No
29 | HIGH | T-23206 | 28 Britton Street, Smithfield | CBIIP 28B Pty Ltd | REVISIT | Gordon Jenkins | Repair | 2098.7851 | 2098.78 | 138 | 2025-11-21 11:06 | No
30 | HIGH | T-21019 | Goodman Fielder - 16 Templar Rd, Erskine Park, NSW | Goodman Fielder Consumer Foo | REVISIT | Gordon Jenkins | Repair | 1893.003 | 1893 | 158 |  | No
31 | HIGH | T-22476 | Pacific Square - 717 Anzac Parade, Maroubra, NSW 2 | Excel Building Management | REVISIT | Nu Unasa | Repair | 1630.63 | 1630.63 | 145 | 2025-11-28 10:00 | No
32 | HIGH | T-19016 | Westlands Industrial Estate - 33-45 James Erskine | Knight Frank | REVISIT | Gordon Jenkins | Repair | 1560.006 | 1560.01 | 188 | 2025-10-02 12:39 | No
33 | HIGH | T-07534 | Rural Fire Brigade - 42 Lamb Street, Glendenning, | Jones Lang LaSalle (NSW) Pty | REVISIT | Haider Al-Heyoury | Callout | 1600 | 1600 | 427 | 2026-01-08 10:00 | No
34 | HIGH | T-23039 | 77 Scott Avenue, Leura, NSW 2780 | Yao Kai Pty Ltd | REVISIT | Gordon Jenkins | Repair | 1195.282 | 1195.28 | 139 | 2025-11-26 11:00 | No
35 | HIGH | T-12719 | 20-22 Mons Road, Westmead, NSW 2145 | Barwon Investment Partners P | REVISIT | Gordon Jenkins | Repair | 1067.006 | 1067.01 | 295 | 2025-09-23 07:00 | No
36 | HIGH | T-26206 | Goodman AU877 - Silverwater D/C - Light & Wonder - | Goodman Property Services (A | REVISIT | Gordon Jenkins | Repair | 1040.004 | 1040 | 111 | 2026-01-30 08:10 | No
37 | HIGH | T-25088 | Goodman AU210 - Gateway Industrial Estate - Buildi | Goodman Property Services (A | REVISIT | Nu Unasa | Repair | 1040.001 | 1040 | 124 | 2026-01-30 06:00 | No
38 | HIGH | T-12700 | Goodman AU099 - 31 Heathcote Road, Moorebank, NSW, | Goodman Property Services (A | REVISIT | Gordon Jenkins | Repair | 1040.004 | 1040 | 298 | 2026-02-05 12:00 | No
39 | HIGH | T-22478 | SP 74790 - The Panorama - 717 Anzac Parade Maroub | Excel Building Management | REVISIT | Nu Unasa | Repair | 843.5 | 843.5 | 145 | 2025-11-28 13:00 | No
40 | HIGH | T-13526 | SP 722 - 167 Victoria Road, Bellevue Hill, NSW 202 | Strata Plan 722 | REVISIT | Nu Unasa | Repair | 800.003 | 800 | 280 | 2025-07-16 07:15 | No
41 | HIGH | T-25090 | Mercedes Benz - 43-47 O’Riordan Street, Alexandria | LSH Auto (Sydney) Pty Ltd | REVISIT | Nu Unasa | Repair | 734.001 | 734 | 124 | 2025-12-16 09:00 | No
42 | HIGH | T-24611 | De Luxe - 7 Blackfriars Street, Chippendale, NSW 2 | DS Holdings and de Luxe Nomi | REVISIT | John Minai | Repair | 342.0024 | 342 | 127 | 2025-12-09 09:00 | No
43 | HIGH | T-27443 | ARBOUR - 63-65 Burrows Road, Alexandria, NSW 2015 | Arbor Property | REVISIT | Nu Unasa | Repair | 292 | 292 | 92 | 2026-01-19 14:00 | No
44 | HIGH | T-07539 | 49 Hotham Parade, Artarmon, NSW 2064 | Jones Lang LaSalle (NSW) Pty | REVISIT | John Minai | Callout | 0 | 3900 | 427 | 2025-08-06 07:51 | No
45 | HIGH | T-00939 | 63 Britton Street, Smithfield, NSW 2164 | C/- Commercial Portfolio Man | REVISIT | John Minai | Callout | 0 | 2837 | 551 | 2025-06-27 10:30 | No
46 | HIGH | T-19704 | The Kitchenary - 27 Holbeche Road, Arndell Park, N | The Kitchenary Pty Ltd | READY | Gordon Jenkins | Repair | 4030.39 | 4030.39 | 176 |  | No
47 | HIGH | T-19670 | Linfox Workshop Service Centre - 65 Lenore Drive, | Linfox Australia | READY |  | Repair | 3278 | 3278 | 179 |  | No
48 | HIGH | T-19049 | Compass Centre - 85 North Terrace Bankstown, NSW 2 | Knight Frank | READY |  | Repair | 3104 | 3104 | 187 |  | No
49 | HIGH | T-15516 | 88 Phillip Street, Parramatta, NSW 2150 | AM Property Plus C/- IOOF In | READY | Gordon Jenkins | Repair | 2780.003 | 2780 | 238 | 2025-08-21 08:00 | No
50 | HIGH | T-15015 | 11 Hexham Place, Wetherill Park, NSW 2164 | CSOF Sub Trust No. 2 ABN 52 | READY | Gordon Jenkins | Repair | 2360 | 2360 | 249 |  | No
51 | HIGH | T-10160 | Northcote Pottery Australia - 2 Distribution Place | Grand Hill Pty Ltd | READY |  | Repair | 1970 | 1970 | 361 |  | No
52 | HIGH | T-14357 | Zirco Data - 1 Johnson Road, Campbelltown, NSW 25 | Lendlease Funds Management L | READY |  | Repair | 6400 |  | 252 |  | No
53 | HIGH | T-13935 | Australasia Chambers - 2 Martin Place, Sydney, NSW | Paspaley Pearls Properties P | REVISIT | John Minai | Repair | 1200 |  | 264 | 2025-07-21 07:00 | No
54 | HIGH | T-26500 | (ROC) Rail Operations Centre - Mandible & Wyndham | Sydney Trains | REVISIT | Nu Unasa | Callout | 580 |  | 107 |  | No
55 | HIGH | T-20626 | 49 Hotham Parade, Artarmon, NSW 2064 | Lendlease Real Estate Invest | REVISIT | Nu Unasa | Callout | 460 |  | 162 | 2025-10-27 14:15 | No
56 | HIGH | T-20075 | Union NSW - 4-10 Goulburn Street, Sydney, NSW 2000 | C/- Colliers Int’l Pty Ltd | REVISIT | Nu Unasa | Callout | 460 |  | 173 | 2025-10-20 08:00 | No
57 | HIGH | T-25477 | Woolworths - Building 1 Kiaora Lands - 1 Kiaora R | C/- Colliers Int’l Pty Ltd | REVISIT | Nu Unasa | Callout | 460 |  | 118 | 2025-12-10 12:30 | No
58 | HIGH | T-19801 | Costas - 4 Beach Street, Eastern Creek, NSW 2766 | Jones Lang LaSalle (NSW) Pty | REVISIT | Nu Unasa | Callout | 460 |  | 176 | 2026-01-09 10:00 | No
59 | HIGH | T-22187 | ACU - Building 600-650 - 25a Baker Road, Strathfie | Australian Catholic Universi | REVISIT | Nu Unasa | Callout | 460 |  | 148 | 2025-11-12 06:00 | No
60 | HIGH | T-07541 | Zirco Data - 1 Johnson Road, Campbelltown, NSW 25 | Lendlease Funds Management L | READY |  | Callout | 130 | 4900 | 427 |  | No
61 | HIGH | T-31022 | YORKAY - 131 York Street, Sydney, NSW 2000 | C/- MMJ Sydney Pty Ltd | REVISIT | Nu Unasa | Repair | 4947.5221 | 4947.53 | 60 | 2026-03-03 06:00 | No
62 | HIGH | T-07536 | Silverwater Industrial Park - Corner Fariola St, | Jones Lang LaSalle (NSW) Pty | READY | John Minai | Callout | 0 | 3300 | 427 | 2025-06-26 07:00 | No
63 | HIGH | T-29184 | Sebel - 48 Airds Road, Minto, NSW 2566 | KNAPP & Associates | REVISIT | Gordon Jenkins | Repair | 4630.008 | 4630.01 | 76 | 2026-01-27 09:56 | No
64 | HIGH | T-31757 | D.J.Wear - 117 York Street, Sydney, NSW 2000 | 117 York Street Pty Limited | REVISIT | Nu Unasa | Repair | 4568.813 | 4568.8 | 50 | 2026-02-25 08:30 | No
65 | HIGH | T-30824 | Goodman AU002 - Slough Business Park - 2 Slough Av | Goodman Property Services (A | REVISIT | John Minai | Repair | 3435.009 | 3435.01 | 62 | 2026-02-24 10:45 | No
66 | HIGH | T-07533 | 28 Percival Road, Smithfield, NSW 2164 | Jones Lang LaSalle (NSW) Pty | READY |  | Callout | 3300 |  | 427 |  | No
67 | HIGH | T-31417 | Cotton King - 95 Bonds Road, Punchbowl, NSW 2196 | Uturn Reuse Pty Limited | REVISIT | Gordon Jenkins | Repair | 3133.2258 | 3133.22 | 55 | 2026-02-23 06:00 | No
68 | HIGH | T-33542 | Building B1, B2, B3 - 5 Williamson Rd, Ingleburn N | Ingleburn Industrial Propert | REVISIT | Gordon Jenkins | Repair | 3183.004 | 3183 | 35 | 2026-03-06 10:00 | No
69 | HIGH | T-32774 | Toll - 11A Greenhills Avenue, Moorebank, NSW 2170 | Vassk Investments Pty Ltd AT | REVISIT | Nick Hollingsworth | Repair | 2388.008 | 2388 | 39 | 2026-03-05 11:36 | No
70 | HIGH | T-28546 | ACU - Building 502 - 40 Edward Street, North Sydne | Australian Catholic Universi | REVISIT | Gordon Jenkins | Repair | 2431.2052 | 2431.2 | 83 | 2026-02-02 06:00 | No
71 | HIGH | T-31091 | Linfox - 3 Harris Avenue, Marsden Park, NSW 2765 | Linfox Australia | REVISIT | Gordon Jenkins | Repair | 2340 | 2340 | 57 | 2026-02-27 06:00 | No
72 | HIGH | T-31974 | Club Ashfield - 1-11 Charlotte Street, Ashfield, N | Ashfield Catholic & Communit | REVISIT | John Minai | Repair | 2425.8222 | 2425.82 | 48 | 2026-03-18 06:00 | No
73 | HIGH | T-34390 | Goodman AU240 - Park View Business Park - 3 Talave | Goodman Property Services (A | REVISIT | Gordon Jenkins | Repair | 7392.3055 | 7392.3 | 28 | 2026-03-26 07:01 | No
74 | HIGH | T-31153 | Linfox - 3 Harris Avenue, Marsden Park, NSW 2765 | Linfox Australia | REVISIT | John Minai | Repair | 2050.005 | 2050 | 57 | 2026-02-17 06:00 | No
75 | HIGH | T-29386 | 30 Loftus Road, Yennora , NSW 2161 | West Infill Sub TC PTY LTD A | REVISIT | Gordon Jenkins | Repair | 2069.927 | 2069.93 | 74 | 2026-02-05 09:28 | No
76 | HIGH | T-28547 | ACU - Building 520 - 3 Berry Street, North Sydney, | Australian Catholic Universi | REVISIT | Nu Unasa | Repair | 1560.006 | 1560.01 | 83 | 2026-02-02 10:00 | No
77 | HIGH | T-29685 | N&A & ACR - 10-12 Distribution Drive, Orchard Hill | TCAL ATF Altis Bulky Sub Tru | REVISIT | Gordon Jenkins | Repair | 1315.8271 | 1315.83 | 69 | 2026-02-03 13:21 | No
78 | HIGH | T-33494 | Space 207 - 207 Pacific Highway, St Leonards, NSW | Altis Bulky Retail ATF Altis | REVISIT | John Minai | Repair | 1040 | 1040 | 36 | 2026-03-09 06:00 | No
79 | HIGH | T-32615 | PFM Corp (BLDG 2) - 147-151 Newton Road, Wetherill | Kenneth R Moras Property Hol | REVISIT | John Minai | Repair | 1040.004 | 1040 | 41 | 2026-03-12 06:00 | No
80 | HIGH | T-32351 | Goodman AU002 - Slough Business Park - Block A Uni | Goodman Property Services (A | REVISIT | John Minai | Repair | 650 | 650 | 43 | 2026-02-24 11:00 | No
81 | HIGH | T-33860 | City of Parramatta Council - 9 Wentworth Street, P | C/- Colliers Int’l Pty Ltd | REVISIT | Nu Unasa | Repair | 520.002 | 520 | 33 | 2026-04-10 11:00 | No
82 | HIGH | T-36512 | COLES RRM - 54 Templar Road, Erskine Park, NSW 275 | Retail Ready Operations Aust | READY |  | Repair | 9692 | 9692 | 12 |  | No
83 | HIGH | T-26567 | 28 Rodborough Road, Frenchs Forest, NSW 2086 | C/- TGC | SCHEDULED |  | Repair | 7976.342 | 7976.34 | 106 | 2026-01-09 06:00 | No
84 | HIGH | T-21783 | TRS - 170 Newton Road, Wetherill Park, NSW 2164 | Newton Road Holdings Pty Ltd | SCHEDULED | Gordon Jenkins | Repair | 7796 | 7796 | 154 | 2026-09-25 06:00 | No
85 | HIGH | T-11638 | Bronson & Jacobs - 70 Marple Avenue, Villawood, NS | George Vasili & Nick Vasili | SCHEDULED |  | Repair | 7105.15 | 7105.15 | 326 | 2026-03-16 06:00 | No
86 | HIGH | T-33571 | FlameSafe Rydalmere Office - Unit 2, 8-10 Mary Pa | FlameSafe Fire Protection (T | REVISIT |  | Callout | 2217 |  | 35 |  | No
87 | HIGH | T-38842 | 15-19 McPherson St, Banksmeadow, NSW 2019 | Roth Industrial | REVISIT | Gordon Jenkins | Repair | 1660 | 1660 | -1 | 2026-04-09 07:00 | No
88 | HIGH | T-35837 | Metrolink Corporate Park - 197-201 Coward Street | The Trust Company (Australia | REVISIT | Gordon Jenkins | Callout | 6340 |  | 18 | 2026-03-23 07:00 | No
89 | HIGH | T-31520 | Metrolink Corporate Park - 197-201 Coward Street | The Trust Company (Australia | REVISIT | Nu Unasa | Callout | 1320 |  | 54 | 2026-02-12 09:00 | No
90 | HIGH | T-36078 | Silverwater Industrial Park - Corner Fariola St, | Lendlease Real Estate Invest | REVISIT | Gordon Jenkins | Repair | 1040.004 | 1040 | 14 | 2026-04-14 06:00 | No
91 | HIGH | T-11659 | CEVA - 9-11 Distribution Drive, Orchard Hills, NSW | TCAL ATF Altis Bulky Sub Tru | SCHEDULED |  | Repair | 5980 | 5980 | 322 | 2025-06-25 06:45 | No
92 | HIGH | T-24771 | Goodman AU058 - Bungaribee Industrial Estate - 71 | Goodman Property Services (A | SCHEDULED |  | Repair | 5786.554 | 5786.55 | 125 | 2025-12-10 10:00 | No
93 | HIGH | T-28579 | 7 Box Road, Taren Point, NSW 2229 | 7 Box Sub TC Pty Ltd ATF 7 B | READY |  | Repair | 650.0025 | 650 | 82 |  | No
94 | HIGH | T-30722 | Costas - 4 Beach Street, Eastern Creek, NSW 2766 | Lendlease Real Estate Invest | REVISIT | John Minai | Callout | 580 |  | 63 | 2026-02-03 15:30 | No
95 | HIGH | T-36205 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ | REVISIT | Gordon Jenkins | Repair | 590 | 590 | 13 | 2026-03-25 11:30 | No
96 | HIGH | T-32785 | Goodman AU181 -Homemaker Centre - 49-59 O'Riordan | Goodman Property Services (A | REVISIT | Nu Unasa | Callout | 460 |  | 39 | 2026-03-02 12:40 | No
97 | HIGH | T-32314 | Goodman AU181 -Homemaker Centre - 49-59 O'Riordan | Goodman Property Services (A | REVISIT | Nu Unasa | Callout | 460 |  | 43 | 2026-02-27 14:00 | No
98 | HIGH | T-32311 | 45 Jones Street St, Ultimo, NSW 2007 | Serbale Pty Limited | REVISIT | Nu Unasa | Callout | 460 |  | 43 | 2026-02-23 12:00 | No
99 | HIGH | T-33545 | LOGOS - Building 5 - 145 Hollinsworth Road, Marsde | Logos Property Management Pt | REVISIT | Gordon Jenkins | Callout | 460 |  | 35 | 2026-03-03 14:00 | No
100 | HIGH | T-31451 | 39A268 - 2-14 Elsie Street, BURWOOD, 2134 | RAM Australia Elseie Street | REVISIT | Nu Unasa | Callout | 460 |  | 55 | 2026-02-19 10:20 | No
101 | HIGH | T-32309 | 40 Ricketty Road, Mascot, NSW 2020 | Henderson & Horning Pty Ltd | REVISIT | Nu Unasa | Callout | 460 |  | 43 | 2026-02-23 06:00 | No
102 | HIGH | T-36204 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ | REVISIT | Gordon Jenkins | Repair | 520 | 520 | 13 | 2026-03-25 07:30 | No
103 | HIGH | T-32771 | Goodman AU106 - M5 Industry Park - Building 2B/2C | Goodman Property Services (A | REVISIT | John Minai | Callout | 460 |  | 39 | 2026-02-27 10:00 | No
104 | HIGH | T-31634 | (ROC) Rail Operations Centre - Mandible & Wyndham | Sydney Trains | REVISIT | Nu Unasa | Callout | 460 |  | 53 | 2026-02-20 10:00 | No
105 | HIGH | T-30699 | Pacific Square - 717 Anzac Parade, Maroubra, NSW 2 | Charter Hall Holdings Pty Lt | REVISIT | Nu Unasa | Callout | 0 |  | 63 | 2026-02-20 06:25 | No
106 | HIGH | T-33570 | Goodman - AU821 City West Office Park - Buildings | Goodman Property Services (A | REVISIT | Nu Unasa | Callout | 0 |  | 35 | 2026-03-04 07:00 | No
107 | HIGH | T-39040 | Goodman AU019 - Transtech Business Park - 12 Mars | Goodman Property Services (A | READY |  | Repair | 4972 | 4972 | -1 |  | No
108 | HIGH | T-28489 | Pacific Square - 717 Anzac Parade, Maroubra, NSW 2 | Excel Building Management | REVISIT | Nu Unasa | Callout | 0 |  | 83 | 2026-02-25 10:00 | No
109 | MEDIUM | T-38941 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ | READY |  | Repair | 4575.2 | 4575.2 | -1 |  | No
110 | MEDIUM | T-09968 | 1A The Crescent, Kingsgrove, NSW 2208 | Vanessa Aus Sub TC Pty Ltd A | SCHEDULED | Nu Unasa | Repair | 4195.004 | 4195 | 364 | 2025-09-19 09:00 | No
111 | MEDIUM | T-36070 | Goodman AU059 - Lidcombe Business Park - Building | Goodman Property Services (A | READY |  | Repair | 3900 | 3900 | 14 |  | No
112 | MEDIUM | T-35278 | 609-615 Harris Street, Ultimo, NSW 2007 | Clara & Matthew Pty Ltd | READY |  | Repair | 3700.006 | 3700.01 | 21 |  | No
113 | MEDIUM | T-38380 | Australasia Chambers - 2 Martin Place, Sydney, NSW | Paspaley Pearls Properties P | READY |  | Repair | 3585.008 | 3585.01 | 5 |  | No
114 | MEDIUM | T-26708 | Goodman AU546 - Interlink Industrial Estate - 28 S | Goodman Property Services (A | SCHEDULED | Gordon Jenkins | Repair | 3555.9162 | 3555.91 | 99 | 2026-01-21 10:00 | No
115 | MEDIUM | T-03094 | LOGOS - Sigma Healthcare - 2 Imperata Close, Kemps | Logos Property Management Pt | SCHEDULED |  | Repair | 3000 | 3000 | 495 | 2025-06-27 07:00 | No
116 | MEDIUM | T-22247 | SP 722 - 167 Victoria Road, Bellevue Hill, NSW 202 | Strata Plan 722 | SCHEDULED | Darren Brailey | Repair | 2554.432 | 2554.43 | 147 | 2025-11-27 12:00 | No
117 | MEDIUM | T-39042 | Goodman AU877 - Silverwater D/C - Light & Wonder - | Goodman Property Services (A | READY |  | Repair | 2390 | 2390 | -1 |  | No
118 | MEDIUM | T-23236 | Storhub - 128 Milperra Road, Revesby, NSW 2212 | StorHub Australia | SCHEDULED |  | Repair | 2335.608 | 2335.61 | 138 | 2025-12-08 06:00 | No
119 | MEDIUM | T-38611 | White Horse - 381 Crown St, Surry Hills | PDC Tech Pty Ltd | READY |  | Repair | 2380.003 | 2380 | 0 |  | Yes
120 | MEDIUM | T-17666 | Costas - 4 Beach Street, Eastern Creek, NSW 2766 | Jones Lang LaSalle (NSW) Pty | SCHEDULED |  | Repair | 2267.884 | 2267.88 | 204 | 2025-09-25 07:00 | No
121 | MEDIUM | T-33543 | ACU - Building 533 - 33 Berry Street, North Sydney | Knight Frank | INPROGRESS | Nu Unasa | Repair | 1740 | 1160 | 35 | 2026-03-21 08:00 | No
122 | MEDIUM | T-17897 | Andrews Meats - 38 Birnie Avenue, Lidcombe, NSW 21 | Andrews Meat Industries Pty | SCHEDULED |  | Repair | 1560 | 1560 | 200 | 2025-10-14 14:00 | No
123 | MEDIUM | T-14097 | AUSTCOR - 159-163 Newton Road Wetherell Park, NSW | Aliro Trusco 1 Pty Ltd ATF t | SCHEDULED | Gordon Jenkins | Repair | 1630 | 1630 | 257 | 2025-11-24 09:00 | No
124 | MEDIUM | T-36568 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ | READY |  | Repair | 1027 | 1027 | 12 |  | No
125 | MEDIUM | T-36567 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ | READY |  | Repair | 1027 | 1027 | 12 |  | No
126 | MEDIUM | T-09362 | LOGOS - Unitrans - 2-4 Harvey Road, Kings Park, N | Logos Property Management Pt | SCHEDULED |  | Callout | 5900 |  | 376 | 2025-05-30 07:00 | No
127 | MEDIUM | T-22477 | SP 74405 - The Northerly - 717 Anzac Parade Marou | Excel Building Management | SCHEDULED | Gordon Jenkins | Repair | 843.5 | 843.5 | 145 | 2025-11-28 12:00 | No
128 | MEDIUM | T-32310 | NKS - 2 Eden Park Drive, Macquarie Park, NSW 2113 | Nks (NSW) Pty Ltd C/- Dunnet | INPROGRESS | Hugo | Repair | 680.63 | 1161.26 | 43 | 2026-02-23 12:00 | No
129 | MEDIUM | T-35245 | Goodman AU543 - 33-38 Quarry Road (Bld B, Bld C & | Goodman Property Services (A | REVISIT | Hugo | Callout | 580 |  | 22 | 2026-03-16 16:00 | No
130 | MEDIUM | T-12518 | 2A / 2B Culverston Road, Minto, NSW, 2566 | The Trust Company Limited in | SCHEDULED | Nu Unasa | Repair | 590 | 590 | 307 | 2025-09-15 09:00 | No
131 | MEDIUM | T-31857 | The Kitchenary - 27 Holbeche Road, Arndell Park, N | The Kitchenary Pty Ltd | READY |  | Callout | 580 |  | 49 |  | No
132 | MEDIUM | T-37325 | ACU - Building 600-650 - 25a Baker Road, Strathfie | Australian Catholic Universi | REVISIT | Gordon Jenkins | Callout | 460 |  | 7 | 2026-04-07 07:00 | No
133 | MEDIUM | T-34621 | Blacktown City Council - 81-85 Flushcombe Road, Bl | Stanton Hillier Parker | REVISIT | Gordon Jenkins | Callout | 460 |  | 26 | 2026-03-12 13:00 | No
134 | MEDIUM | T-34151 | 40 Ricketty Road, Mascot, NSW 2020 | Henderson & Horning Pty Ltd | REVISIT | John Minai | Callout | 460 |  | 29 | 2026-03-10 06:00 | No
135 | MEDIUM | T-38790 | LOGOS - Sigma Healthcare - 2 Imperata Close, Kemps | Logos Property Management Pt | READY |  | Repair | 520.002 | 520 | 0 |  | No
136 | MEDIUM | T-36796 | Goodman AU059 Lidcombe Business Park (Buildings A | Goodman Property Services (A | REVISIT | Darren Brailey | Callout | 460 |  | 11 | 2026-03-27 13:10 | No
137 | MEDIUM | T-35114 | ACU - Building 600-650 - 25a Baker Road, Strathfie | Australian Catholic Universi | REVISIT | Gordon Jenkins | Callout | 130 |  | 22 | 2026-03-24 08:30 | No
138 | MEDIUM | T-35777 | Coles CFC - 154 Cowpasture Road, Wetherill Park, N | The Trustee for Charter Hall | REVISIT | Darren Brailey | Callout | 0 |  | 19 | 2026-03-24 05:30 | No
139 | MEDIUM | T-14356 | 36 Honeycomb Drive, Eastern Creek, NSW 2766 | Jones Lang LaSalle (NSW) Pty | SCHEDULED |  | Repair | 3500 |  | 252 | 2025-10-14 11:00 | No
140 | MEDIUM | T-12842 | Royal Life Saving Academy - 47 Lovell Road, Denist | Royal Life Saving NSW | SCHEDULED | John Minai | Callout | 920 |  | 292 | 2025-07-10 11:00 | No
141 | MEDIUM | T-31534 | Emirates - L17 - 1 York Street, Sydney, NSW 2000 | Emirates | INPROGRESS | Nu Unasa | Callout | 460 |  | 54 | 2026-02-13 08:00 | No
142 | MEDIUM | T-26652 | Goodman AU545 - Interlink Industrial Estate - Kimb | Goodman Property Services (A | SCHEDULED | Ryan Robinson | Callout | 460 |  | 104 | 2025-12-24 06:00 | No
143 | MEDIUM | T-32782 | 11A & 11B Grand Avenue, Camellia, NSW 2142 | Asia Property AU 1 ATF the C | INPROGRESS | Hugo | Callout | 460 |  | 39 | 2026-03-02 12:00 | No
144 | MEDIUM | T-20077 | 11-13 Orion Road, Lane Cove West, NSW 2066 | The Trustee for Gemstone Lan | SCHEDULED |  | Callout | 460 |  | 173 | 2025-10-21 10:00 | No
145 | MEDIUM | T-38908 | 85 Waterloo Road, Macquarie Park NSW 2113 | Goodman Property Services (A | READY |  | Callout | 460 |  | -1 |  | No
146 | MEDIUM | T-36098 | Goodman AU019 - Transtech Business Park - 12 Mars | Goodman Property Services (A | READY |  | Callout | 0 |  | 14 |  | No
147 | MEDIUM | T-38875 | Goodman AU019 - Transtech Business Park - 12 Mars | Goodman Property Services (A | READY |  | Callout | 0 |  | -1 |  | No
148 | MEDIUM | T-10320 | By the Bay Investments - 2 Giffnock Avenue, North | ESSC, REM Colliers Internati | SCHEDULED |  | Callout | 0 |  | 348 | 2026-02-19 14:00 | No
149 | MEDIUM | T-36635 | COLES RRM - 54 Templar Road, Erskine Park, NSW 275 | Retail Ready Operations Aust | SCHEDULED |  | Repair | 9587.818 | 9587.82 | 11 | 2026-05-05 06:00 | No
150 | MEDIUM | T-28601 | Ya Zhou Wen Hua Enterprises - 541-543 Kent Street, | C/- ED Realty | SCHEDULED |  | Repair | 4174.009 | 4174.01 | 82 | 2026-02-06 06:00 | No
151 | MEDIUM | T-28480 | State Library of NSW - 1 Shakespeare Place, Sydney | State Library of NSW | SCHEDULED |  | Repair | 3906.208 | 3906.21 | 83 | 2026-01-16 06:00 | No
152 | MEDIUM | T-32509 | 26 Nelson Road, Yennora, NSW 2161 | The Trust Company (Australia | SCHEDULED |  | Repair | 3283.2348 | 3283.24 | 42 | 2026-04-23 06:00 | No
153 | MEDIUM | T-33531 | Mandarin Centre - 65 Albert Ave, Chatswood NSW 206 | Mandarin Developments Pty Lt | SCHEDULED |  | Repair | 2865.004 | 2865 | 35 | 2026-04-14 06:00 | No
154 | MEDIUM | T-31681 | KB House - 72-76 Archer Street, Chatswood, NSW 206 | Shead Real Estate Pty Ltd | SCHEDULED |  | Repair | 1985 | 1985 | 53 | 2026-02-18 06:00 | No
155 | MEDIUM | T-32610 | Goodman AU820 - City West Office Park - Building A | Goodman Property Services (A | SCHEDULED |  | Repair | 1670.762 | 1670.76 | 41 | 2026-04-27 06:00 | No
156 | MEDIUM | T-36072 | Space 207 - 207 Pacific Highway, St Leonards, NSW | Altis Bulky Retail ATF Altis | SCHEDULED |  | Repair | 5673.04 | 5673.04 | 14 | 2026-04-29 06:00 | No
157 | MEDIUM | T-32692 | Precinct 5 AU186 - 3 Tundra Close, Kemps Kreek, NS | Goodman Property Services (A | SCHEDULED |  | Repair | 660.513 | 660.51 | 40 | 2026-03-11 12:00 | No
158 | MEDIUM | T-36961 | Landhop Chatswood - 11 Spring Street, Chatswood, N | Landhop Pty Ltd | INPROGRESS | Hugo | Callout | 580 |  | 11 | 2026-03-27 16:00 | No
159 | MEDIUM | T-38942 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ | SCHEDULED |  | Repair | 5238.4 | 5238.4 | -1 |  | No
160 | MEDIUM | T-37163 | 1 YORK - 1 York Street, Sydney, NSW 2000 | York II Sub Trust | INPROGRESS | Hugo | Callout | 0 |  | 8 | 2026-03-30 17:30 | No
161 | MEDIUM | T-36829 | Gateway Business Park - Unit 3/9/10 - 63-79 Parram | Cambooya Properties C/o Knig | SCHEDULED |  | Repair | 3190 | 3190 | 11 | 2026-04-08 07:00 | No
162 | MEDIUM | T-34915 | 11-13 Orion Road, Lane Cove West, NSW 2066 | The Trustee for Gemstone Lan | SCHEDULED |  | Repair | 1753.9506 | 1753.96 | 25 | 2026-04-28 06:00 | No
163 | MEDIUM | T-36467 | Goodman AU059 Lidcombe Business Park (Buildings A | Goodman Property Services (A | SCHEDULED |  | Repair | 1733.413 | 1733.41 | 12 | 2026-05-01 06:00 | No
164 | MEDIUM | T-37159 | Jacfin Ricoh - 4 Telopea Place, Eastern Creek, NS | FlameSafe Warranty (Contract | SCHEDULED |  | Repair | 1325.0025 | 1325 | 8 | 2026-04-13 06:00 | No
165 | MEDIUM | T-34395 | PPIF - 9 George Street, Parramatta, NSW 2150 | Talish Property Group C/- Kn | SCHEDULED |  | Repair | 780.003 | 780 | 28 | 2026-03-25 08:00 | No
166 | MEDIUM | T-35708 | NIMBE - 39-47 Regent Street, Chippendale, NSW 2008 | Intera Group | SCHEDULED |  | Repair | 700.102 | 700.1 | 19 | 2026-03-26 10:00 | No
167 | MEDIUM | T-36631 | Freight Assist Australia - 26 Pavesi Street, Guild | Cambooya Properties C/- Knig | SCHEDULED |  | Repair | 650.0025 | 650 | 11 | 2026-05-04 06:00 | No
168 | MEDIUM | T-36074 | Labour Council of NSW - 377-383 Sussex Street, Syd | Unions NSW Property and Serv | SCHEDULED |  | Repair | 460 | 460 | 14 | 2026-04-30 06:00 | No
169 | MEDIUM | T-32680 | 372-394 Elizabeth Street, Surry Hills, NSW 2010 | Contec Properties Pty Ltd | SCHEDULED |  | Callout | 460 |  | 40 | 2026-03-25 10:15 | No
170 | MEDIUM | T-28602 | Goodman AU122 - Showground Business Park 12 - 20 A | Goodman Property Services (A | SCHEDULED |  | Callout | 460 |  | 82 | 2026-01-15 06:00 | No
171 | MEDIUM | T-35710 | ACU - Building 526 - 8-10 Berry Street, North Sydn | Australian Catholic Universi | SCHEDULED |  | Repair | 520.002 | 520 | 19 | 2026-03-27 09:00 | No
172 | MEDIUM | T-38182 | Kraft Heinz - 92-96 Station Road, Seven Hills, NSW | Kraft-Heinz Co Australia Ltd | SCHEDULED |  | Repair | 460 | 460 | 5 | 2026-04-07 12:00 | No
173 | MEDIUM | T-33437 | State Library of NSW - 1 Shakespeare Place, Sydney | State Library of NSW | SCHEDULED |  | Callout | 330 |  | 36 | 2026-03-27 06:00 | No
174 | MEDIUM | T-39238 | Goodman AU106 - M5 Industry Park - Building 1 - 1 | Goodman Property Services (A | SCHEDULED |  | Repair | 0 | 1818.5 | -2 | 2026-04-10 12:00 | No
175 | LOW | T-34751 | State Library of NSW - 1 Shakespeare Place, Sydney | State Library of NSW | SCHEDULED |  | Callout | 580 |  | 25 | 2026-03-18 06:00 | No
176 | LOW | T-36073 | 1 YORK - 1 York Street, Sydney, NSW 2000 | York II Sub Trust | SCHEDULED |  | Callout | 460 |  | 14 | 2026-04-10 06:00 | No
177 | LOW | T-35477 | ACU - Building 532 - 8-20 Napier Street, North Syd | Australian Catholic Universi | SCHEDULED |  | Callout | 460 |  | 20 | 2026-03-20 13:00 | No
178 | LOW | T-38249 | 223-225 Liverpool Street, Darlinghurst, NSW 2010 | Forza Capital Pty Ltd ATF Fo | SCHEDULED | Gordon Jenkins | Callout | 460 |  | 5 | 2026-04-10 07:00 | No
179 | LOW | T-36636 | Metrolink Corporate Park - 197-201 Coward Street | The Trust Company (Australia | SCHEDULED |  | Callout | 460 |  | 11 | 2026-04-27 10:00 | No
179 of 179 tasks shown | [7 empty] | 512648.1139 | 465575.16

## QUOTES
Flamesafe Fire — Quote Register · 08 April 2026
52 finalised $279,221 · 26 submitted $120,317 · Win rate: 60% · Avg margin: 23.3%
REF | PROPERTY | CLIENT | STATUS | DATE | DUE DATE | REVENUE ($) | MARGIN % | TOTAL INC GST | DESCRIPTION
QD-1586 | JOY Building - 78 Kent Road, Mascot NSW 2020 | Logos Property Management Pty Li | FINALISED | 2025-10-15 | 2025-11-15 | 74380.75 | 27.91% | 81818.82 | Gas system - reinstate
QD-2312 | 63 Jedda Road, Prestons, NSW 2170 | Vanilla Australian Sub II TC Pty | DRAFT | 2026-02-13 | 2026-03-13 | 66371.14 | 22.34% | 73008.25 | AFSS Inspection report
QD-2456 - FIP | Goodman AU106 - M5 Industry Park - Building 2 | Goodman Property Services (Aust) | SUBMITTED | 2026-03-04 | 2026-04-04 | 49962.79 | 25.36% | 54959.07 | Fire Equipment repairs
QD-1329 | 2-14 Elsie Street | MAXAM & CO | FINALISED | 2025-09-01 | 2025-10-01 | 15538.63 | 21.11% | 17092.49 | IVFA Fitout
QD-2239 - FIP | Northcote Pottery Australia - 2 Distribution | Grand Hill Pty Ltd | SUBMITTED | 2026-02-03 | 2026-03-03 | 13354.1 | 17.26% | 14689.51 | End of Life FIP Replacement
QD-2322 - FIP | SP 52948 Macquarie Gardens - 1-15 Fontenoy Ro | Waratah Strata Management | FINALISED | 2026-02-16 | 2026-03-16 | 12618.23 | 23.73% | 13880.14 | Annual Detector failure
QD-2249 - FIP | 87 Marsden Street, Parramatta, NSW 2150 | MHPHA Marsden Street Pty Ltd | FINALISED | 2026-02-05 | 2026-03-05 | 11760.01 | 20.07% | 12936.01 | AFSS Inspection report January
QD-1383 | 10 Julius Ave, North Ryde NSW, 2113 | Logos Property Management Pty Li | FINALISED | 2025-09-08 | 2025-10-08 | 11410 | 22.81% | 12551 | 5 Yearly Detection and Warning System
QD-2442 | Goodman AU543 - Zirco Data - 15-23 Quarry Roa | Goodman Property Services (Aust) | DRAFT | 2026-03-02 | 2026-04-02 | 8874.41 | 29.05% | 9761.85 | Replacement of the faulty Vesda #3
QD-2610 - FIP | 1A The Crescent, Kingsgrove, NSW 2208 | Vanessa Aus Sub TC Pty Ltd ATF V | FINALISED | 2026-03-27 | 2026-04-27 | 8840.02 | 23.98% | 9724.02 | FIP APFS defect repairs/inspection Feb 2026
QD-2508 - FIP | Goodman Fielder - 16 Templar Rd, Erskine Park | Goodman Fielder Consumer Foods P | FINALISED | 2026-03-11 | 2026-04-11 | 6764.41 | 20.6% | 7440.85 | FIP AFSS Inspection report Feb 26
QD-0307(v2) | Pacific Square - 717 Anzac Parade, Maroubra, | Excel Building Management | SUBMITTED | 2026-04-02 |  | 6532.76 | 29.63% | 7186.02 | Monthly Defect - Battery
QD-2457 - GAS | 8 Priddle Street, Warwick Farm, NSW 2170 | Rathdrum Properties Pty Ltd | FINALISED | 2026-03-04 | 2026-04-04 | 6396 | 23.08% | 7035.6 | AFSS - Passive Fire Sealing
QD-2647 - FIP | Impact International - Cnr Victoria and O’Con | Impact International | FINALISED | 2026-04-01 | 2026-05-01 | 5968.97 | 16.51% | 6565.87 | FIP AFSS inspection report Feb 2026
QD-2377 - FIP | 112 Wharf Road, Melrose Park, NSW 2114 | C/- Colliers Int’l Pty Ltd | FINALISED | 2026-02-23 | 2026-03-23 | 5714.83 | 16.69% | 6286.31 | FIP AFSS Inspection report Jan 2026
QD-2482 - FIP | Buildings A, B & C - 29 Davis Road, Wetherill | Lendlease Real Estate Investment | FINALISED | 2026-03-06 | 2026-04-06 | 5702.97 | 23.2% | 6273.27 | AFSS FIP defect report Feb 2026
QD-1410 | 10a Julius Ave, North Ryde NSW 2113, | Logos Property Management Pty Li | FINALISED | 2025-09-09 | 2025-10-09 | 5410 | 22.81% | 5951 | 5 Yearly Detection and Warning System
QD-2640 - FIP | LOGOS - Unitrans - 2-4 Harvey Road, Kings Pa | Logos Property Management Pty Li | FINALISED | 2026-03-31 | 2026-04-30 | 5076.01 | 16.82% | 5583.61 | FIP Annual defect repairs/investigation
QD-1136 | 83-87 Market Street, Sydney, NSW 2000 | Mercer Property Pty Ltd | FINALISED | 2025-07-30 | 2025-08-30 | 4420.01 | 16.06% | 4862.01 | AFSS Inspection Report 09072025
QD-1381 | 205-231 Fairfield Rd, Guildford West, NSW 216 | Logos Property Management Pty Li | FINALISED | 2025-09-08 | 2025-10-08 | 4220 | 22.91% | 4642 | 5 Yearly Detection and Warning System
QD-2510 - FIP | Bodium - 487 Elizabeth Street, Surry Hills, N | Bodium Property Pty Ltd | FINALISED | 2026-03-11 | 2026-04-11 | 4189.9 | 22.08% | 4608.89 | AFSS Defect report Feb 2026
QD-1344 | Goodman AU058 - Bungaribee Industrial Estate | Goodman Property Services (Aust) | FINALISED | 2025-09-02 | 2025-10-02 | 3930 | 23.38% | 4323 | 5 Yearly Detection and Warning System
QD-2254 | Blackwoods - 1-3 Bellevue Circuit, Greystanes | Blackwoods | SUBMITTED | 2026-02-06 | 2026-03-06 | 3882.69 | 22.25% | 4270.96 | Horn speakers installation
QD-1384 | 16 Rodborough Rd, Frenchs Forest, NSW 2086 | Logos Property Management Pty Li | FINALISED | 2025-09-08 | 2025-10-08 | 3820 | 22.96% | 4202 | 5 Yearly Detection and Warning System
QD-2439 | Goodman AU646 - 146 O'Riordan Street, Mascot, | Goodman Property Services (Aust) | SUBMITTED | 2026-03-02 | 2026-04-02 | 3754.99 | 23.31% | 4130.49 | FIP Replacement of faulty detectors
QD-2650 | 63 Britton Street, Smithfield, NSW 2164 | C/- Commercial Portfolio Managem | SUBMITTED | 2026-04-01 | 2026-05-01 | 3140 | 22.53% | 3454 | Defects identified during the Annual Fire Safety Inspec
QD-2085 | JOY Building - 78 Kent Road, Mascot NSW 2020 | Logos Property Management Pty Li | SUBMITTED | 2026-01-09 | 2026-02-09 | 2988.2 | 20.32% | 3287.02 | Monthly defect repairs required
QD-2398 - FIP | ACU - Building 502 - 40 Edward Street, North | Australian Catholic Universities | SUBMITTED | 2026-02-24 | 2026-03-24 | 2941.08 | 24.23% | 3235.18 | FIP Annual Defect repairs/investigation
QD-1510 | JOY Building - 78 Kent Road, Mascot NSW 2020 | Logos Property Management Pty Li | FINALISED | 2025-09-30 | 2025-10-30 | 2903.42 | 17.98% | 3193.76 | AFSS Inspection Report September 2025
QD-2641 - FIP | Ingal Civil Products - 57-65 Airds Road, Mint | Ingal Civil Products | FINALISED | 2026-03-31 | 2026-04-30 | 2849.01 | 19.62% | 3133.91 | FIP AFSS Inspection report Feb 2026
QD-2207 - FIP | LOGOS - 1 Monier Square, Villawood - NSW 2165 | Logos Property Management Pty Li | FINALISED | 2026-01-29 | 2026-02-28 | 2700 | 19.37% | 2970 | AFSS inspection Report
QD-2540 | Union NSW - 4-10 Goulburn Street, Sydney, NSW | C/- Colliers Int’l Pty Ltd | FINALISED | 2026-03-16 | 2026-04-16 | 2696 | 20.88% | 2965.6 | AFSS Inspection Report Feb 2026
QD-2642 - FIP | Bucher Municipal - 19 Astoria Road Marsden P | Ganian Pty Ltd ATF Blacktown Was | FINALISED | 2026-03-31 | 2026-04-30 | 2622 | 20.29% | 2884.2 | FIP AFSS inspection Report Feb 2026
QD-2480 - FIP | 82 Belmore Road North, Riverwood, NSW 2210 | Lendlease Real Estate Investment | FINALISED | 2026-03-06 | 2026-04-06 | 2602.96 | 15.92% | 2863.26 | AFSS FIP defect report Feb 2026
QD-2210 - FIP | Pro-Pac Packaging (BLDG 1) - 147 Newton Road, | Kenneth R Moras Property Holding | FINALISED | 2026-01-30 | 2026-02-28 | 2404.4 | 21.19% | 2644.84 | AFSS Inspection report
QD-2651 | Goodman AU877 - Silverwater D/C - Light & Won | Goodman Property Services (Aust) | SUBMITTED | 2026-04-01 | 2026-05-01 | 2390 | 14.23% | 2629 | Defects identified during the Monthly Fire Panel Testin
QD-1468 | White Horse - 381 Crown St, Surry Hills | PDC Tech Pty Ltd | FINALISED | 2025-09-16 | 2026-06-30 | 2380 | 29.03% | 2618 | Faulty card replacement - FIP repairs
QD-2213 _ FIP | Visy Recycling - 112 Euston Road, Alexandria, | Lendlease Real Estate Investment | SUBMITTED | 2026-01-30 | 2026-02-28 | 2330.01 | 23.99% | 2563.01 | Monthly Vesda defects
QD-2432 | 26 Nelson Road, Yennora, NSW 2161 | The Trust Company (Australia) Li | SUBMITTED | 2026-02-27 | 2026-03-27 | 2261.92 | 23.2% | 2488.11 | FIP AFSS Defect repairs
QD-1686 | 20 Eastern Creek Drive, Eastern Creek, NSW 27 | Bieson Pty Ltd C/- CBRE Pty Ltd | DRAFT | 2025-11-03 | 2025-12-03 | 2227 | 19.29% | 2449.7 | Overrides fire pump fan
QD-2549 - FIP | Goodman AU543 - Packcentre Shed 2 - 33-83 Qua | Goodman Property Services (Aust) | FINALISED | 2026-03-17 | 2026-04-17 | 2200 | 17.73% | 2420 | AFSS Inspection report March 2026
QD-2574 - FIP (39418) | Goodman AU543 - Zirco Data - 15-23 Quarry Roa | Goodman Property Services (Aust) | FINALISED | 2026-03-23 | 2026-04-23 | 2180.8 | 16.91% | 2398.88 | FIP AFSS Inspection Report March 2026 - 39418
QD-1338 | GoodmanAU079 Greystanes Park East - (BLDG 4) | Goodman Property Services (Aust) | FINALISED | 2025-09-02 | 2025-10-02 | 2124 | 22.98% | 2336.4 | 5 Yearly Detection and Warning System
QD-1334 | Goodman AU870 - Chep - 13-15 Interchange Driv | Goodman Property Services (Aust) | FINALISED | 2025-09-02 | 2025-10-02 | 2094 | 23.83% | 2303.4 | 5 Yearly Detection and Warning System
QD-2638 - FIP | Centuria - K&S Freighters - 1 Hope Street, St | Centuria Institutional Investmen | FINALISED | 2026-03-31 | 2026-04-30 | 2084.01 | 20.68% | 2292.41 | FIP Annual Defect repairs/investigation
QD-2553 | 91 Phillip Street, Parramatta, NSW 2150 | REI Property Sub Pty Ltd ATF REI | FINALISED | 2026-03-17 | 2026-04-17 | 2082.54 | 23.84% | 2290.79 | AFSS Inspection Report Feb 2026
QD-2466 | ACU - Building 600-650 - 25a Baker Road, Stra | Australian Catholic Universities | SUBMITTED | 2026-03-05 | 2026-04-05 | 2080.01 | 19.23% | 2288.01 | Investigation of Earth fault
QD-2550 - FIP | Goodman AU543 - 33-38 Quarry Road , Erskine P | Goodman Property Services (Aust) | FINALISED | 2026-03-17 | 2026-04-17 | 2052.79 | 19.99% | 2258.07 | AFSS Inspection report March 2026 Building B & C
QD-2124 | Goodman AU002 - Slough Business Park - Block | Goodman Property Services (Aust) | SUBMITTED | 2026-01-16 | 2026-02-16 | 2030 | 20.2% | 2233 | Replacement/removal of faulty domestic detector
QD-1323 | Barangaroo Culture Space Building - Cnr Towns | c/- Cushman & Wakefield Pty Ltd | FINALISED | 2025-08-29 | 2025-09-29 | 1870 | 17.43% | 2057 | AFSS Inspection Report August 2025
QD-1641 | 67 West Street, North Sydney, NSW 2055 | S & E Cuccurullo | FINALISED | 2025-10-23 | 2025-11-23 | 1800 | 11.11% | 1980 | AFSS Inspection Report October 2025
QD-1483 | TRS - 170 Newton Road, Wetherill Park, NSW 21 | Newton Road Holdings Pty Ltd | FINALISED | 2025-09-19 | 2025-10-19 | 1712.5 | 22.34% | 1883.75 | AFSS Inspection Report September 2025
QD-2468 | Australian Red Cross Lifeblood - 17 O'Riordan | Australian Red Cross Lifeblood | SUBMITTED | 2026-03-05 | 2026-04-05 | 1696.48 | 26% | 1866.13 | FIP Monthly battery defect
QD-2370 | LOGOS - Building 7 - 145 Hollinsworth Road, M | Logos Property Management Pty Li | SUBMITTED | 2026-02-20 | 2026-03-20 | 1670.3 | 24.97% | 1837.33 | Fault repairs
QD-1606 | Visy Recycling - 112 Euston Road, Alexandria, | Lendlease Real Estate Investment | FINALISED | 2025-10-17 | 2025-11-17 | 1630 | 23.01% | 1793 | AFSS Inspection Report September 2025
QD-2478 - FIP | Goodman AU643 - 15 Berry Street, Granville, N | Goodman Property Services (Aust) | FINALISED | 2026-03-06 | 2026-04-06 | 1607 | 20.35% | 1767.7 | AFSS FIP Defect report Feb 2026
QD-2609 - FIP | 20-22 Mons Road, Westmead, NSW 2145 | Barwon Investment Partners Pty L | SUBMITTED | 2026-03-27 | 2026-04-27 | 1587 | 22.94% | 1745.7 | FIP Monthly defect repairs
QD-1375 | ACU - Building 533 - 33 Berry Street, North S | Australian Catholic Universities | FINALISED | 2025-09-04 | 2025-10-04 | 1308.2 | 22.55% | 1439.02 | FAIL SAFE DEVICES rectification
QD-2622 | 15 Distribution Dr. Orchard Hills | Knight Frank | SUBMITTED | 2026-03-30 | 2026-04-30 | 1270 | 15.75% | 1397 | Mechanical controls programming
QD-2429 - FIP | Linfox - 27-49 Lenore Drive, Erskine Park, NS | Linfox - Erskine Park Health Ca | FINALISED | 2026-02-27 | 2026-03-27 | 1270 | 15.75% | 1397 | FIP AFSS Defect repairs Feb 2026
QD-2551 - FIP (APFS) | Goodman AU543 - 33-38 Quarry Road , Erskine P | Goodman Property Services (Aust) | FINALISED | 2026-03-17 | 2026-04-17 | 1265 | 20.95% | 1391.5 | AFSS Inspection report Mar 2026 Building D
QD-1342 | AU079 Greystanes Park East - (BLDG 2) Marshal | Goodman Property Services (Aust) | FINALISED | 2025-09-02 | 2025-10-02 | 1190 | 23.03% | 1309 | 5 yearly FIP/OWS
QD-2474 | 49 Hotham Parade, Artarmon, NSW 2064 | Lendlease Real Estate Investment | SUBMITTED | 2026-03-06 | 2026-04-06 | 1171 | 20.41% | 1288.1 | Critical FIP Defects from Monthly testing
QD-2605 | 2A / 2B Culverston Road, Minto, NSW, 2566 | The Trust Company Limited in its | FINALISED | 2026-03-26 | 2026-04-26 | 1040 | 19.23% | 1144 | FIP - Annual defect repairs/investigation
QD-0927 | Rickoh - 364-372 Kent Street, Sydney, NSW 200 | Mercer Property Pty Ltd | FINALISED | 2025-06-06 | 2025-07-06 | 1040 | 19.23% | 1144 | APFS Report 2025 - Detection and Warning System
QD-2045 | Centuria - 8 Hexham Place, Wetherill Park, NS | Centuria Property Funds No. 2 Lt | FINALISED | 2026-01-06 | 2026-02-06 | 1040 | 19.23% | 1144 | AFSS inspection report repairs December 2025
QD-1064 | Mandarin Centre - 65 Albert Ave, Chatswood NS | Mandarin Developments Pty Ltd C- | FINALISED | 2025-07-08 | 2025-08-08 | 980 | 35.71% | 1078 | Monthly Defect July 2025 - Panel Fault
QD-2250 | 3M - L3 Computer Room - 1A Rivett Road, North | Jones Lang LaSalle (NSW) Pty Ltd | SUBMITTED | 2026-02-05 | 2026-03-05 | 950.35 | 22.63% | 1045.39 | Monthly defect inspection
QD-2530 | 20-22 Mons Road, Westmead, NSW 2145 | Barwon Investment Partners Pty L | SUBMITTED | 2026-03-13 | 2026-04-13 | 942.86 | 21.09% | 1037.15 | Vesda fault rectification
QD-1273 | Labour Council of NSW - 377-383 Sussex Street | Unions NSW Property and Services | FINALISED | 2025-08-18 | 2025-09-18 | 920 | 54.35% | 1012 | Fire Detector isolations and deisolations
QD-2614 - FIP (Ann) | Goodman AU543 - 33-38 Quarry Road , Erskine P | Goodman Property Services (Aust) | FINALISED | 2026-03-27 | 2026-04-27 | 657.43 | 24.88% | 723.17 | FIP Annual defect repairs
QD-2020 | VERTIX - 311 South Street, Marsden Park NSW 2 | FlameSafe Warranty (Contracts) | FINALISED | 2025-12-30 | 2026-01-30 | 650 | 19.23% | 715 | Monthly Defect - Comm Fault
QD-2462 - FIP | Goodman AU019 - Transtech Business Park - 12 | Goodman Property Services (Aust) | FINALISED | 2026-03-05 | 2026-04-05 | 650 | 19.23% | 715 | FIP AFSS Inspection report Feb 2026
QD-1395 | DLP 31 Heinrich Close, Eastern Creek | FlameSafe Warranty (Contracts) | FINALISED | 2025-09-09 | 2025-10-09 | 610 | 46.97% | 671 | Monthly Testing July 2025
QD-2391 | Goodman AU646 - 146 O'Riordan Street, Mascot, | Goodman Property Services (Aust) | SUBMITTED | 2026-02-24 | 2026-03-24 | 520 | 19.23% | 572 | End of Life FIP replacement
QD-2575 | LOGOS - Sigma Healthcare - 2 Imperata Close, | Logos Property Management Pty Li | SUBMITTED | 2026-03-23 | 2026-04-23 | 520 | 19.23% | 572 | FIP Monthly Defect repairs
QD-2089 - FIP | Resolution X - 21B Richmond Road, Homebush We | Cranden Investments Pty Ltd | SUBMITTED | 2026-01-09 | 2026-02-09 | 469.99 | 23.85% | 516.99 | Monthly Battery Defect repairs
QD-1065 | Goodman AU058 - Bungaribee Industrial Estate | Goodman Property Services (Aust) | FINALISED | 2025-07-08 | 2025-08-08 | 460 | 54.35% | 506 | Monthly Defect July 2025 - Panel Fault
QD-2325 | Veolia Water Treatment Plant - 1 East Parade | Veolia Water Operations Pty Ltd | SUBMITTED | 2026-02-16 | 2026-03-16 | 460 | 54.35% | 506 | FIP Investigation
QD-1654 | Goodman AU106 - M5 Industry Park - Building 1 | Goodman Property Services (Aust) | DRAFT | 2025-10-27 | 2025-11-27 | 421.06 | 23.19% | 463.17 | Monthly Testing October 2025
QD-2412 | 1 Rivett Road, North Ryde, NSW 2113 | Quality Green Metro Pty Ltd as T | SUBMITTED | 2026-02-25 | 2026-03-25 | 343 | 21.87% | 377.3 | FIP Monthly battery Defects
QD-2646 | Goodman AU543 - 15-23 Quarry Road, Erskine Pa | Goodman Property Services (Aust) | DRAFT | 2026-04-01 | 2026-05-01 | 260 | 94.15% | 286 | Monthly Defect March - FIP door Broken
QD-2362 - FIP | Bucher Municipal - 19 Astoria Road Marsden P | Ganian Pty Ltd ATF Blacktown Was | SUBMITTED | 2026-02-19 | 2026-03-19 | 130 | 19.23% | 143 | Annual testing critical Defect
QD-2445 | LAPP - 12 Grevillea Street, Eastern Creek, N | Tammatali Pty Ltd as Trustee for | DRAFT | 2026-03-03 | 2026-04-03 | 0 | 0% | 0 | FIP Monthly Battery defects
QD-1340 | Goodman AU079 Greystanes Park East - (BLDG 3) | Goodman Property Services (Aust) | DRAFT | 2025-09-02 | 2025-10-02 | 0 | 0% | 0 | 5 Yearly Detection and Warning System
QD-1260 | Goodman AU181 -Homemaker Centre - 49-59 O'Ri | Goodman Property Services (Aust) | DRAFT | 2025-08-14 | 2025-09-14 | 0 | 0% | 0 | Monthly Testing August 2025
86 of 86 quotes | [5 empty] | 441369.94 | 22.92% | 485506.99

## DASHBOARD
Flamesafe Fire — Operations Dashboard
08 April 2026 · Must quote $297,692/month to hit $180k · Win rate: 60% · Margin: 23.3%
FINANCIAL SNAPSHOT
| TASK PIPELINE |  | FINALISED QUOTES |  | SUBMITTED QUOTES |  |  | REPAIR VALUE |  | INVOICED |  | MONTHLY TARGET
| 523608.1045 |  | 279220.55 |  | 120317.47 |  |  | 458889.1045 |  | 8214.7161 |  | 180000
TASK STATUS · What needs doing
| STATUS | COUNT | VALUE ($) | % TOTAL | AVG VALUE ($) | NEXT ACTION
| REVISIT | 95 | 290074.1548 | 55.4% | 3053.4122 | Quote / Schedule repairs
| SCHEDULED | 51 | 138384.8546 | 26.43% | 2713.4285 | Confirm tech before date
| READY | 27 | 80268.4745 | 15.33% | 2972.9065 | Assign technician now
| INPROGRESS | 6 | 3920.63 | 0.7488% | 653.4383 | Follow up — on site
| PERFORMED | 31 | 10959.9906 | 2.093% | 353.5481 | Raise invoice
REVENUE MODEL · Win rate 60% · Must quote $297,692/month
| METRIC | CURRENT | TARGET | GAP | STATUS
| Monthly Revenue | 27922.055 | 180000 | -152077.945 | ✗ BELOW
| Monthly Quoting | 48550.699 | 297692.3077 | -249141.6087 | ✗ BELOW
| Quote Multiplier | 60.47% | 70% | -9.535% | ✗ BELOW
| Gross Margin | 23.34% | 25% | -1.662% | ✗ BELOW
TECHNICIAN WORKLOAD · 11 Technicians
| TECHNICIAN | TASKS | VALUE ($) | REPAIRS | CALLOUTS | REVISITS | READY | SCHEDULED | CRITICAL | HIGH | %
| Gordon Jenkins | 60 | 187069.4637 | 39 | 21 | 34 | 3 | 5 | 6 | 29 | 35.73%
| Nu Unasa | 43 | 95413.8742 | 22 | 21 | 35 | 0 | 3 | 2 | 34 | 18.22%
| John Minai | 22 | 38765.8736 | 12 | 10 | 17 | 1 | 1 | 1 | 16 | 7.404%
| Bailey Arthur | 1 | 12263.736 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 2.342%
| Darren Brailey | 9 | 7205.442 | 3 | 6 | 3 | 0 | 1 | 0 | 1 | 1.376%
| Ryan Robinson | 2 | 2988.0025 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0.5707%
| Nick Hollingsworth | 1 | 2388.008 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0.4561%
| Hugo | 5 | 2300.63 | 1 | 4 | 1 | 0 | 0 | 0 | 0 | 0.4394%
| Haider Al-Heyoury | 1 | 1600 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0.3056%
| Tim Hu | 1 | 469.9906 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08976%
| Jimmy Kak | 1 | 130 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0.02483%

## ANALYTICS
Flamesafe Fire — Revenue & Margin Analytics · Mathematical Target Model
Target: $180,000/month · Win rate: 60% · Avg quote: $5,370 · Avg margin: 23.3% · Must quote: $297,692/month to collect $180k
CORE BUSINESS METRICS · Actual vs Target
| MONTHLY TARGET |  | ACTUAL MONTHLY REVENUE | REVENUE GAP |  | WIN RATE |  | AVG FINALISED QUOTE |  | AVG GROSS MARGIN
| 180000 |  | 27922.055 | 152077.945 |  | 60.47% |  | 5369.626 |  | 23.34%
| Revenue to collect per month |  | $152,078 below target — estimated from finalised quotes over 10 months | Shortfall vs target each month |  | 52 won of 86 total quotes |  | Average value of a quote you win |  | Target: 25%+ · Currently 23.3%
⚡ KEY INSIGHT: You quote ~$48,551/month. At your 60% win rate that yields ~$29,356/month revenue. To collect $180,000/month you must quote $297,692/month — that is $249,142/month MORE than current rate. Quote multiplier = 1.65x.
THE QUOTE MULTIPLIER · At 60% win rate: to earn $180k you must quote $297,692/month (1.65x)
| WIN RATE SCENARIO |  | MUST QUOTE/MONTH ($) | QUOTES NEEDED (@ avg $5,370) | vs CURRENT QUOTING |  | REVENUE COLLECTED |  | vs $180k TARGET
| 50% — Very conservative |  | 360000 | 67.0438 | 311449.301 |  | 24275.3495 |  | -155724.6505
| 55% — Conservative |  | 327272.7273 | 60.9489 | 278722.0283 |  | 26702.8845 |  | -153297.1155
| 60% — Moderate |  | 300000 | 55.8698 | 251449.301 |  | 29130.4194 |  | -150869.5806
| 60% — Your actual rate |  | 297692.3077 | 55.44 | 249141.6087 |  | 29356.2366 |  | -150643.7634
| 65% — Improved conversion |  | 276923.0769 | 51.5721 | 228372.3779 |  | 31557.9543 |  | -148442.0456
| 70% — Strong conversion |  | 257142.8571 | 47.8884 | 208592.1581 |  | 33985.4893 |  | -146014.5107
| 75% — Excellent conversion |  | 240000 | 44.6959 | 191449.301 |  | 36413.0243 |  | -143586.9758
| 80% — Best case |  | 225000 | 41.9024 | 176449.301 |  | 38840.5592 |  | -141159.4408
QUOTE SIZE vs VOLUME · How many quotes needed per month at $297,692 target volume
| AVG QUOTE SIZE |  | QUOTES NEEDED/MONTH | vs CURRENT PACE | ANN. REVENUE AT TARGET |  | OPERATIONAL FEASIBILITY
| Low — $3k avg |  | 99.2308 | 90.189 | 2160000 |  | High volume
| Below avg — $4k |  | 74.4231 | 65.3813 | 2160000 |  | High volume
| Near avg — $5k |  | 59.5385 | 50.4967 | 2160000 |  | High volume
| Current avg — $5,370 |  | 55.44 | 46.3983 | 2160000 |  | High volume
| Good — $6k avg |  | 49.6154 | 40.5737 | 2160000 |  | High volume
| Strong — $7k avg |  | 42.5275 | 33.4857 | 2160000 |  | High volume
| High — $8k avg |  | 37.2115 | 28.1698 | 2160000 |  | High volume
| Premium — $10k avg |  | 29.7692 | 20.7275 | 2160000 |  | Achievable
REVENUE BRIDGE · Where the money is and what action unlocks it
| REVENUE BUCKET |  |  | VALUE ($) | PRIORITY |  | ACTION REQUIRED
| WORK PERFORMED — awaiting invoice |  |  | 10959.9906 | IMMEDIATE |  | 30 tasks completed. Raise invoices immediately — cash is ready to collect.
| WORK IN PROGRESS — technician on site |  |  | 3920.63 | THIS WEEK |  | 7 tasks currently being worked. Follow up technicians for completion.
| READY — no technician assigned yet |  |  | 67871.2745 | THIS WEEK |  | 18 tasks approved, dispatching needed. $67,871 sitting idle.
| SCHEDULED — booked and upcoming |  |  | 133146.4546 | THIS MONTH |  | 52 tasks booked in. Will convert on completion and invoicing.
| SUBMITTED QUOTES — awaiting authorisation |  |  | 120317.47 | THIS MONTH |  | 26 quotes pending. Chase authorisation to unlock.
| AUTHORISED BACKLOG — schedule pending |  |  | 324588.4293 | NEXT 30 DAYS |  | 63 authorised revisit tasks need scheduling. Quote approved, just needs a date.
| TOTAL ACCESSIBLE REVENUE |  |  | 660804.249
MARGIN TARGET ANALYSIS · Current: 23.3% · Each 1% improvement = $4,414 more gross profit
| MARGIN TARGET |  | GROSS PROFIT ($) | vs CURRENT GP ($) | COST NEEDED ($) |  | MONTHLY GP
| 20% — Below current |  | 88273.988 | -14730.992 | 353095.952 |  | 8827.3988
| 22% — Slightly below |  | 97101.3868 | -5903.5932 | 344268.5532 |  | 9710.1387
| 23.3% — Current actual |  | 103004.98 | 0 | 338364.96 |  | 10300.498
| 25% — Industry benchmark |  | 110342.485 | 7337.505 | 331027.455 |  | 11034.2485
| 27% — Good |  | 119169.8838 | 16164.9038 | 322200.0562 |  | 11916.9884
| 30% — Strong |  | 132410.982 | 29406.002 | 308958.958 |  | 13241.0982
| 35% — Excellent |  | 154479.479 | 51474.499 | 286890.461 |  | 15447.9479
MONTHLY REVENUE ACTUALS · Finalised quote value by month vs $180k target
| MONTH |  | QUOTES RAISED | TOTAL QUOTED ($) | FINALISED REV ($) |  | vs $180k |  | ATTAINMENT
| 2025-06 |  | 1 | 1144 | 1144 |  | -178856 |  | 0.6356%
| 2025-07 |  | 3 | 6446.01 | 6446.01 |  | -173553.99 |  | 3.581%
| 2025-08 |  | 3 | 3069 | 3069 |  | -176931 |  | 1.705%
| 2025-09 |  | 15 | 64515.82 | 64515.82 |  | -115484.18 |  | 35.84%
| 2025-10 |  | 4 | 86054.99 | 85591.82 |  | -94408.18 |  | 47.55%
| 2025-11 |  | 1 | 2449.7 | 0 |  | -180000 |  | 0%
| 2025-12 |  | 1 | 715 | 715 |  | -179285 |  | 0.3972%
| 2026-01 |  | 7 | 15358.86 | 6758.84 |  | -173241.16 |  | 3.755%
| 2026-02 |  | 15 | 136672.49 | 34499.46 |  | -145500.54 |  | 19.17%
| 2026-03 |  | 31 | 148960.23 | 69914.73 |  | -110085.27 |  | 38.84%
| 2026-04 |  | 5 | 20120.89 | 6565.87 |  | -173434.13 |  | 3.648%
| 0 |  | 0 | 0 | 0 |  | 0 |  | 0%
WHAT NEEDS TO CHANGE · Ranked by revenue impact — the 4 levers to hit $180k/month
| # | LEVER |  | DETAIL |  |  | IMPACT ($) |  | PRIORITY
| 1 | INCREASE QUOTE VOLUME |  | Quoting $48,551/month — need $297,692/month. That is 55 quotes/month vs ~9 current. |  |  | 249141.6087 |  | CRITICAL
| 2 | INVOICE COMPLETED WORK |  | 31 tasks PERFORMED and not invoiced. Value: $10,960. This money is earned — raise invoices now. |  |  | 10959.9906 |  | IMMEDIATE
| 3 | DISPATCH READY TASKS |  | 24 tasks READY but unassigned. Value: $67,871. Assigning a tech turns these into revenue this month. |  |  | 67871.2745 |  | THIS WEEK
| 4 | IMPROVE GROSS MARGIN |  | At 23.3% margin, every 1% improvement = $4,414 more GP. Target 25% adds $7,338 to gross profit. |  |  | 4413.6994 |  | ONGOING

## FINANCIAL
FLAMESAFE FIRE · Financial Analysis & Budget Tracker
Monthly target: $180,000 · April 2026
CORE ASSUMPTIONS & TARGETS
| METRIC | VALUE ($) | % OF TARGET | NOTES / SOURCE
| Monthly Revenue Target ($) | 180000 | 100% | Blue = editable input — change to model scenarios
| Total Pipeline — All Tasks | 503202.5045 | 279.6% | Sum of Task Value across all 196 tasks in Uptick
| Quotes Submitted — Value | 120317.47 | 66.84% | 26 quotes awaiting client approval
| Quotes Finalised — Value | 279220.55 | 155.1% | 52 quotes won and approved
| Repair Tasks — Total Value | 439403.5045 | 244.1% | 124 repair tasks
| Callout Tasks — Total Value | 63799 | 35.44% | 81 callout tasks
| Invoiced This Period | 8214.7161 | 4.564% | Tasks marked Invoiced in Uptick billing module
| Target Attainment — Finalised | 66.84% |  | Finalised quote value ÷ monthly target
| Target Attainment — Invoiced | 35.44% |  | Invoiced value ÷ monthly target
| Pipeline Coverage Ratio | 1 |  | Total pipeline ÷ monthly target
QUOTE FINANCIAL BREAKDOWN · Material / Labour / Margin Analysis
| STATUS | QUOTE COUNT | SUBTOTAL | TOTAL COST | GROSS MARGIN % | TOTAL (INC GST)
| DRAFT | 8 | 78153.61 | 59975.62 | 23.5% | 85968.97
| FINALISED | 52 | 253836.8 | 194659.44 | 22.81% | 279220.55
| SUBMITTED | 26 | 109379.53 | 83729.9 | 22.97% | 120317.47
| TOTAL | 86 | 441369.94 | 338364.96 | 23.09% | 485506.99
BUDGET & COST TRACKING · Repairs / Labour / Materials
| COST CATEGORY | BUDGET ($) | ACTUAL ($) | VARIANCE ($) | % USED | STATUS
| Labour — Field Technicians | 45000 | 25519.6 | -19480.4 | 56.71% | On Track
| Materials — Detection Devices | 25000 | 0 | -25000 | 0% | Under Budget
| Materials — Ancillary/Consumables | 8000 | 0 | -8000 | 0% | Under Budget
| Subcontractor / Contractor Costs | 15000 | 0 | -15000 | 0% | Under Budget
| Vehicle & Travel | 6000 | 0 | -6000 | 0% | Under Budget
| Overhead Allocation | 12000 | 0 | -12000 | 0% | Under Budget
| Warranty & Rework Allowance | 5000 | 0 | -5000 | 0% | Under Budget
| TOTAL | 116000 | 25519.6 | -90480.4 | 22%

## SCHEDULE REGISTER
Flamesafe Fire — Schedule Register · 180 Scheduled Tasks
Sorted by date · ⚠ OVERLAP = same tech same day · Totals update with filters
# | REF | PROPERTY | CLIENT | TECH | STATUS | SCHED DATE | VALUE ($) | OVERLAP? | CATEGORY | DAYS OPEN
1 | T-05579 | 1 Wentworth Street, Parramatta, NSW 2150 | N G P Investments (no 2) Pty | Darren Brailey | REVISIT | 2025-01-10 12:32 | 2351.01 |  | Repair | 454
2 | T-00911 | 203-209 Northumberland Street, Liverpool - NS | Inner West Council C/- Knigh | Nu Unasa | SCHEDULED | 2025-01-24 12:00 | 15682 |  | Callout | 551
3 | T-09869 | Impact International - Cnr Victoria and O’Con | Impact International | Bailey Arthur | REVISIT | 2025-04-29 11:55 | 12263.736 |  | Repair | 372
4 | T-09362 | LOGOS - Unitrans - 2-4 Harvey Road, Kings Pa | Logos Property Management Pt |  | SCHEDULED | 2025-05-30 07:00 | 5900 |  | Callout | 376
5 | T-11659 | CEVA - 9-11 Distribution Drive, Orchard Hills | TCAL ATF Altis Bulky Sub Tru |  | SCHEDULED | 2025-06-25 06:45 | 5980 |  | Repair | 322
6 | T-07536 | Silverwater Industrial Park - Corner Fariola | Jones Lang LaSalle (NSW) Pty | John Minai | READY | 2025-06-26 07:00 | 0 |  | Callout | 427
7 | T-03094 | LOGOS - Sigma Healthcare - 2 Imperata Close, | Logos Property Management Pt |  | SCHEDULED | 2025-06-27 07:00 | 3000 |  | Repair | 495
8 | T-00939 | 63 Britton Street, Smithfield, NSW 2164 | C/- Commercial Portfolio Man | John Minai | REVISIT | 2025-06-27 10:30 | 0 |  | Callout | 551
9 | T-12842 | Royal Life Saving Academy - 47 Lovell Road, D | Royal Life Saving NSW | John Minai | SCHEDULED | 2025-07-10 11:00 | 920 |  | Callout | 292
10 | T-13526 | SP 722 - 167 Victoria Road, Bellevue Hill, NS | Strata Plan 722 | Nu Unasa | REVISIT | 2025-07-16 07:15 | 800.003 |  | Repair | 280
11 | T-13935 | Australasia Chambers - 2 Martin Place, Sydney | Paspaley Pearls Properties P | John Minai | REVISIT | 2025-07-21 07:00 | 1200 |  | Repair | 264
12 | T-14463 | Kraft Heinz - 92-96 Station Road, Seven Hills | Kraft-Heinz Co Australia Ltd | Gordon Jenkins | REVISIT | 2025-08-01 09:00 | 10484 |  | Repair | 250
13 | T-07539 | 49 Hotham Parade, Artarmon, NSW 2064 | Jones Lang LaSalle (NSW) Pty | John Minai | REVISIT | 2025-08-06 07:51 | 0 |  | Callout | 427
14 | T-13630 | 49 Hotham Parade, Artarmon, NSW 2064 | Jones Lang LaSalle (NSW) Pty | John Minai | REVISIT | 2025-08-08 13:10 | 2110.0006 |  | Repair | 274
15 | T-15516 | 88 Phillip Street, Parramatta, NSW 2150 | AM Property Plus C/- IOOF In | Gordon Jenkins | READY | 2025-08-21 08:00 | 2780.003 |  | Repair | 238
16 | T-16132 | Australasia Chambers - 2 Martin Place, Sydney | Paspaley Pearls Properties P | Nu Unasa | REVISIT | 2025-09-09 09:00 | 2080 |  | Repair | 225
17 | T-12518 | 2A / 2B Culverston Road, Minto, NSW, 2566 | The Trust Company Limited in | Nu Unasa | SCHEDULED | 2025-09-15 09:00 | 590 |  | Repair | 307
18 | T-17558 | Pengton - 80 George Street, Parramatta, NSW 2 | Pengton No. 1 Pty Ltd ATF Pe | Gordon Jenkins | REVISIT | 2025-09-16 09:00 | 7507.5684 |  | Repair | 207
19 | T-09968 | 1A The Crescent, Kingsgrove, NSW 2208 | Vanessa Aus Sub TC Pty Ltd A | Nu Unasa | SCHEDULED | 2025-09-19 09:00 | 4195.004 |  | Repair | 364
20 | T-17260 | Fred Health & Bleach - 24 Rothschild, Roseber | C/- TGC | Ryan Robinson | REVISIT | 2025-09-19 11:00 | 2528.0025 |  | Repair | 211
21 | T-12719 | 20-22 Mons Road, Westmead, NSW 2145 | Barwon Investment Partners P | Gordon Jenkins | REVISIT | 2025-09-23 07:00 | 1067.006 |  | Repair | 295
22 | T-17666 | Costas - 4 Beach Street, Eastern Creek, NSW 2 | Jones Lang LaSalle (NSW) Pty |  | SCHEDULED | 2025-09-25 07:00 | 2267.884 |  | Repair | 204
23 | T-19016 | Westlands Industrial Estate - 33-45 James Ers | Knight Frank | Gordon Jenkins | REVISIT | 2025-10-02 12:39 | 1560.006 |  | Repair | 188
24 | T-19012 | Ontex - 5 Wonderland Drive, Eastern Creek, NS | One Funds Management Limited | Nu Unasa | REVISIT | 2025-10-08 07:00 | 4728.67 |  | Repair | 188
25 | T-14356 | 36 Honeycomb Drive, Eastern Creek, NSW 2766 | Jones Lang LaSalle (NSW) Pty |  | SCHEDULED | 2025-10-14 11:00 | 3500 |  | Repair | 252
26 | T-17897 | Andrews Meats - 38 Birnie Avenue, Lidcombe, N | Andrews Meat Industries Pty |  | SCHEDULED | 2025-10-14 14:00 | 1560 |  | Repair | 200
27 | T-19273 | Metrolink Corporate Park - 197-201 Coward Str | The Trust Company (Australia | Nu Unasa | REVISIT | 2025-10-16 07:00 | 2895.008 |  | Repair | 181
28 | T-20075 | Union NSW - 4-10 Goulburn Street, Sydney, NSW | C/- Colliers Int’l Pty Ltd | Nu Unasa | REVISIT | 2025-10-20 08:00 | 460 |  | Callout | 173
29 | T-20077 | 11-13 Orion Road, Lane Cove West, NSW 2066 | The Trustee for Gemstone Lan |  | SCHEDULED | 2025-10-21 10:00 | 460 |  | Callout | 173
30 | T-20626 | 49 Hotham Parade, Artarmon, NSW 2064 | Lendlease Real Estate Invest | Nu Unasa | REVISIT | 2025-10-27 14:15 | 460 |  | Callout | 162
31 | T-19009 | MONDC - 13 Bushmaster Avenue, Moorebank, NSW | Primary Connect | Gordon Jenkins | REVISIT | 2025-10-28 07:35 | 14387.3845 |  | Repair | 188
32 | T-20036 | Foothills Distribution Centre - 30 Lidco Stre | The Trustee For Gemstone Arn | Gordon Jenkins | REVISIT | 2025-11-05 07:00 | 13244.1535 |  | Repair | 174
33 | T-20080 | Elizabeth Towers - 418A Elizabeth Street, Su | X Commercial | Nu Unasa | REVISIT | 2025-11-06 07:00 | 7065.508 |  | Repair | 173
34 | T-22187 | ACU - Building 600-650 - 25a Baker Road, Stra | Australian Catholic Universi | Nu Unasa | REVISIT | 2025-11-12 06:00 | 460 |  | Callout | 148
35 | T-23206 | 28 Britton Street, Smithfield | CBIIP 28B Pty Ltd | Gordon Jenkins | REVISIT | 2025-11-21 11:06 | 2098.7851 |  | Repair | 138
36 | T-14097 | AUSTCOR - 159-163 Newton Road Wetherell Park | Aliro Trusco 1 Pty Ltd ATF t | Gordon Jenkins | SCHEDULED | 2025-11-24 09:00 | 1630 |  | Repair | 257
37 | T-23039 | 77 Scott Avenue, Leura, NSW 2780 | Yao Kai Pty Ltd | Gordon Jenkins | REVISIT | 2025-11-26 11:00 | 1195.282 |  | Repair | 139
38 | T-13540 | 223-225 Liverpool Street, Darlinghurst, NSW 2 | Forza Capital Pty Ltd ATF Fo | Gordon Jenkins | REVISIT | 2025-11-27 07:30 | 2628.002 |  | Repair | 279
39 | T-22247 | SP 722 - 167 Victoria Road, Bellevue Hill, NS | Strata Plan 722 | Darren Brailey | SCHEDULED | 2025-11-27 12:00 | 2554.432 |  | Repair | 147
40 | T-22476 | Pacific Square - 717 Anzac Parade, Maroubra, | Excel Building Management | Nu Unasa | REVISIT | 2025-11-28 10:00 | 1630.63 | ⚠ OVERLAP | Repair | 145
41 | T-22477 | SP 74405 - The Northerly - 717 Anzac Parade | Excel Building Management | Gordon Jenkins | SCHEDULED | 2025-11-28 12:00 | 843.5 |  | Repair | 145
42 | T-22478 | SP 74790 - The Panorama - 717 Anzac Parade M | Excel Building Management | Nu Unasa | REVISIT | 2025-11-28 13:00 | 843.5 | ⚠ OVERLAP | Repair | 145
43 | T-23236 | Storhub - 128 Milperra Road, Revesby, NSW 221 | StorHub Australia |  | SCHEDULED | 2025-12-08 06:00 | 2335.608 |  | Repair | 138
44 | T-24611 | De Luxe - 7 Blackfriars Street, Chippendale, | DS Holdings and de Luxe Nomi | John Minai | REVISIT | 2025-12-09 09:00 | 342.0024 |  | Repair | 127
45 | T-24771 | Goodman AU058 - Bungaribee Industrial Estate | Goodman Property Services (A |  | SCHEDULED | 2025-12-10 10:00 | 5786.554 |  | Repair | 125
46 | T-25477 | Woolworths - Building 1 Kiaora Lands - 1 Kia | C/- Colliers Int’l Pty Ltd | Nu Unasa | REVISIT | 2025-12-10 12:30 | 460 |  | Callout | 118
47 | T-25090 | Mercedes Benz - 43-47 O’Riordan Street, Alexa | LSH Auto (Sydney) Pty Ltd | Nu Unasa | REVISIT | 2025-12-16 09:00 | 734.001 |  | Repair | 124
48 | T-16225 | Labour Council of NSW - 377-383 Sussex Street | Unions NSW Property and Serv | John Minai | REVISIT | 2025-12-18 10:00 | 5090 |  | Repair | 223
49 | T-22186 | Union NSW - 4-10 Goulburn Street, Sydney, NSW | C/- Colliers Int’l Pty Ltd | Gordon Jenkins | REVISIT | 2025-12-18 11:00 | 3270 |  | Repair | 148
50 | T-26441 | Metrolink Corporate Park - 197-201 Coward Str | The Trust Company (Australia | Nu Unasa | PERFORMED | 2025-12-20 07:30 | 1160 |  | Callout | 109
51 | T-26652 | Goodman AU545 - Interlink Industrial Estate - | Goodman Property Services (A | Ryan Robinson | SCHEDULED | 2025-12-24 06:00 | 460 |  | Callout | 104
52 | T-26046 | 28 Percival Road, Smithfield, NSW 2164 | Lendlease Real Estate Invest | Nu Unasa | REVISIT | 2026-01-05 08:00 | 10056.493 |  | Repair | 112
53 | T-23677 | Frutex - 20 St Albans Road, Kingsgrove, NSW 2 | Sterilisation Technologies A | Gordon Jenkins | REVISIT | 2026-01-07 06:00 | 4038.228 | ⚠ OVERLAP | Repair | 132
54 | T-12370 | Frutex - 20 St Albans Road, Kingsgrove, NSW 2 | Sterilisation Technologies A | Gordon Jenkins | REVISIT | 2026-01-07 08:17 | 10090.053 | ⚠ OVERLAP | Repair | 312
55 | T-07534 | Rural Fire Brigade - 42 Lamb Street, Glendenn | Jones Lang LaSalle (NSW) Pty | Haider Al-Heyoury | REVISIT | 2026-01-08 10:00 | 1600 |  | Callout | 427
56 | T-26567 | 28 Rodborough Road, Frenchs Forest, NSW 2086 | C/- TGC |  | SCHEDULED | 2026-01-09 06:00 | 7976.342 |  | Repair | 106
57 | T-19801 | Costas - 4 Beach Street, Eastern Creek, NSW 2 | Jones Lang LaSalle (NSW) Pty | Nu Unasa | REVISIT | 2026-01-09 10:00 | 460 |  | Callout | 176
58 | T-28218 | Labour Council of NSW - 377-383 Sussex Street | Unions NSW Property and Serv | Gordon Jenkins | PERFORMED | 2026-01-13 09:00 | 460 |  | Callout | 85
59 | T-28602 | Goodman AU122 - Showground Business Park 12 - | Goodman Property Services (A |  | SCHEDULED | 2026-01-15 06:00 | 460 |  | Callout | 82
60 | T-25885 | 20 Eastern Creek Drive, Eastern Creek, NSW 27 | Healthcare Logistics | Gordon Jenkins | PERFORMED | 2026-01-15 06:00 | 0 |  | Repair | 113
61 | T-28480 | State Library of NSW - 1 Shakespeare Place, S | State Library of NSW |  | SCHEDULED | 2026-01-16 06:00 | 3906.208 |  | Repair | 83
62 | T-27606 | Nine Radio L1 Building C - 33-35 Saunders Str | Radio 2GB Sydney Pty Ltd | Darren Brailey | PERFORMED | 2026-01-16 11:00 | 460 |  | Callout | 90
63 | T-27443 | ARBOUR - 63-65 Burrows Road, Alexandria, NSW | Arbor Property | Nu Unasa | REVISIT | 2026-01-19 14:00 | 292 |  | Repair | 92
64 | T-26708 | Goodman AU546 - Interlink Industrial Estate - | Goodman Property Services (A | Gordon Jenkins | SCHEDULED | 2026-01-21 10:00 | 3555.9162 |  | Repair | 99
65 | T-29184 | Sebel - 48 Airds Road, Minto, NSW 2566 | KNAPP & Associates | Gordon Jenkins | REVISIT | 2026-01-27 09:56 | 4630.008 |  | Repair | 76
66 | T-26002 | ACU - Building 600-650 - 25a Baker Road, Stra | Australian Catholic Universi | Nu Unasa | REVISIT | 2026-01-29 06:00 | 5834.7131 |  | Repair | 113
67 | T-25088 | Goodman AU210 - Gateway Industrial Estate - B | Goodman Property Services (A | Nu Unasa | REVISIT | 2026-01-30 06:00 | 1040.001 |  | Repair | 124
68 | T-26206 | Goodman AU877 - Silverwater D/C - Light & Won | Goodman Property Services (A | Gordon Jenkins | REVISIT | 2026-01-30 08:10 | 1040.004 |  | Repair | 111
69 | T-28546 | ACU - Building 502 - 40 Edward Street, North | Australian Catholic Universi | Gordon Jenkins | REVISIT | 2026-02-02 06:00 | 2431.2052 |  | Repair | 83
70 | T-28547 | ACU - Building 520 - 3 Berry Street, North Sy | Australian Catholic Universi | Nu Unasa | REVISIT | 2026-02-02 10:00 | 1560.006 |  | Repair | 83
71 | T-25482 | Jaycar Electronics Group - 46 Eastern Creek D | Electus Distribution Pty Ltd | John Minai | REVISIT | 2026-02-03 06:00 | 5383.0095 | ⚠ OVERLAP | Repair | 118
72 | T-29685 | N&A & ACR - 10-12 Distribution Drive, Orchard | TCAL ATF Altis Bulky Sub Tru | Gordon Jenkins | REVISIT | 2026-02-03 13:21 | 1315.8271 |  | Repair | 69
73 | T-30722 | Costas - 4 Beach Street, Eastern Creek, NSW 2 | Lendlease Real Estate Invest | John Minai | REVISIT | 2026-02-03 15:30 | 580 | ⚠ OVERLAP | Callout | 63
74 | T-23333 | Foothills Distribution Centre - 30 Lidco Stre | The Trustee For Gemstone Arn | Nu Unasa | REVISIT | 2026-02-05 07:10 | 7430 |  | Repair | 137
75 | T-29386 | 30 Loftus Road, Yennora , NSW 2161 | West Infill Sub TC PTY LTD A | Gordon Jenkins | REVISIT | 2026-02-05 09:28 | 2069.927 | ⚠ OVERLAP | Repair | 74
76 | T-12700 | Goodman AU099 - 31 Heathcote Road, Moorebank, | Goodman Property Services (A | Gordon Jenkins | REVISIT | 2026-02-05 12:00 | 1040.004 | ⚠ OVERLAP | Repair | 298
77 | T-28601 | Ya Zhou Wen Hua Enterprises - 541-543 Kent St | C/- ED Realty |  | SCHEDULED | 2026-02-06 06:00 | 4174.009 |  | Repair | 82
78 | T-31520 | Metrolink Corporate Park - 197-201 Coward Str | The Trust Company (Australia | Nu Unasa | REVISIT | 2026-02-12 09:00 | 1320 |  | Callout | 54
79 | T-31534 | Emirates - L17 - 1 York Street, Sydney, NSW 2 | Emirates | Nu Unasa | INPROGRESS | 2026-02-13 08:00 | 460 |  | Callout | 54
80 | T-31153 | Linfox - 3 Harris Avenue, Marsden Park, NSW 2 | Linfox Australia | John Minai | REVISIT | 2026-02-17 06:00 | 2050.005 |  | Repair | 57
81 | T-31681 | KB House - 72-76 Archer Street, Chatswood, NS | Shead Real Estate Pty Ltd |  | SCHEDULED | 2026-02-18 06:00 | 1985 |  | Repair | 53
82 | T-31451 | 39A268 - 2-14 Elsie Street, BURWOOD, 2134 | RAM Australia Elseie Street | Nu Unasa | REVISIT | 2026-02-19 10:20 | 460 |  | Callout | 55
83 | T-10320 | By the Bay Investments - 2 Giffnock Avenue, N | ESSC, REM Colliers Internati |  | SCHEDULED | 2026-02-19 14:00 | 0 |  | Callout | 348
84 | T-30699 | Pacific Square - 717 Anzac Parade, Maroubra, | Charter Hall Holdings Pty Lt | Nu Unasa | REVISIT | 2026-02-20 06:25 | 0 | ⚠ OVERLAP | Callout | 63
85 | T-31634 | (ROC) Rail Operations Centre - Mandible & Wyn | Sydney Trains | Nu Unasa | REVISIT | 2026-02-20 10:00 | 460 | ⚠ OVERLAP | Callout | 53
86 | T-32190 | COLES RRM - 54 Templar Road, Erskine Park, NS | Retail Ready Operations Aust | Gordon Jenkins | PERFORMED | 2026-02-20 12:00 | 460 |  | Callout | 46
87 | T-31417 | Cotton King - 95 Bonds Road, Punchbowl, NSW | Uturn Reuse Pty Limited | Gordon Jenkins | REVISIT | 2026-02-23 06:00 | 3133.2258 |  | Repair | 55
88 | T-32309 | 40 Ricketty Road, Mascot, NSW 2020 | Henderson & Horning Pty Ltd | Nu Unasa | REVISIT | 2026-02-23 06:00 | 460 | ⚠ OVERLAP | Callout | 43
89 | T-32311 | 45 Jones Street St, Ultimo, NSW 2007 | Serbale Pty Limited | Nu Unasa | REVISIT | 2026-02-23 12:00 | 460 | ⚠ OVERLAP | Callout | 43
90 | T-32310 | NKS - 2 Eden Park Drive, Macquarie Park, NSW | Nks (NSW) Pty Ltd C/- Dunnet | Hugo | INPROGRESS | 2026-02-23 12:00 | 680.63 |  | Repair | 43
91 | T-30824 | Goodman AU002 - Slough Business Park - 2 Slou | Goodman Property Services (A | John Minai | REVISIT | 2026-02-24 10:45 | 3435.009 | ⚠ OVERLAP | Repair | 62
92 | T-32351 | Goodman AU002 - Slough Business Park - Block | Goodman Property Services (A | John Minai | REVISIT | 2026-02-24 11:00 | 650 | ⚠ OVERLAP | Repair | 43
93 | T-31757 | D.J.Wear - 117 York Street, Sydney, NSW 2000 | 117 York Street Pty Limited | Nu Unasa | REVISIT | 2026-02-25 08:30 | 4568.813 | ⚠ OVERLAP | Repair | 50
94 | T-28489 | Pacific Square - 717 Anzac Parade, Maroubra, | Excel Building Management | Nu Unasa | REVISIT | 2026-02-25 10:00 | 0 | ⚠ OVERLAP | Callout | 83
95 | T-32636 | Goodman - AU881- 65 Epping Road, Macquarie Pa | Goodman Property Services (A | Nu Unasa | PERFORMED | 2026-02-25 12:00 | 0 | ⚠ OVERLAP | Callout | 41
96 | T-31091 | Linfox - 3 Harris Avenue, Marsden Park, NSW 2 | Linfox Australia | Gordon Jenkins | REVISIT | 2026-02-27 06:00 | 2340 |  | Repair | 57
97 | T-32771 | Goodman AU106 - M5 Industry Park - Building 2 | Goodman Property Services (A | John Minai | REVISIT | 2026-02-27 10:00 | 460 |  | Callout | 39
98 | T-32314 | Goodman AU181 -Homemaker Centre - 49-59 O'Ri | Goodman Property Services (A | Nu Unasa | REVISIT | 2026-02-27 14:00 | 460 |  | Callout | 43
99 | T-32782 | 11A & 11B Grand Avenue, Camellia, NSW 2142 | Asia Property AU 1 ATF the C | Hugo | INPROGRESS | 2026-03-02 12:00 | 460 |  | Callout | 39
100 | T-32785 | Goodman AU181 -Homemaker Centre - 49-59 O'Ri | Goodman Property Services (A | Nu Unasa | REVISIT | 2026-03-02 12:40 | 460 |  | Callout | 39
101 | T-31022 | YORKAY - 131 York Street, Sydney, NSW 2000 | C/- MMJ Sydney Pty Ltd | Nu Unasa | REVISIT | 2026-03-03 06:00 | 4947.5221 |  | Repair | 60
102 | T-12542 | Pittking Properties - 175-181 Oxford Street, | C/- Steven Krulis Real Estat | John Minai | REVISIT | 2026-03-03 09:05 | 11120.0209 |  | Repair | 305
103 | T-33436 | Veolia Water Treatment Plant - 1 East Parade | Veolia Water Operations Pty | Gordon Jenkins | PERFORMED | 2026-03-03 13:00 | 460 | ⚠ OVERLAP | Callout | 36
104 | T-33545 | LOGOS - Building 5 - 145 Hollinsworth Road, M | Logos Property Management Pt | Gordon Jenkins | REVISIT | 2026-03-03 14:00 | 460 | ⚠ OVERLAP | Callout | 35
105 | T-33570 | Goodman - AU821 City West Office Park - Build | Goodman Property Services (A | Nu Unasa | REVISIT | 2026-03-04 07:00 | 0 |  | Callout | 35
106 | T-33630 | Baxter - 164 Newton Road, Wetherill Park, NSW | Centuria Property Funds No. | Gordon Jenkins | REVISIT | 2026-03-04 12:00 | 13702.25 |  | Repair | 34
107 | T-33795 | Coles CFC - 154 Cowpasture Road, Wetherill Pa | The Trustee for Charter Hall | Nu Unasa | PERFORMED | 2026-03-05 10:00 | 460 |  | Callout | 33
108 | T-32774 | Toll - 11A Greenhills Avenue, Moorebank, NSW | Vassk Investments Pty Ltd AT | Nick Hollingsworth | REVISIT | 2026-03-05 11:36 | 2388.008 |  | Repair | 39
109 | T-33542 | Building B1, B2, B3 - 5 Williamson Rd, Ingleb | Ingleburn Industrial Propert | Gordon Jenkins | REVISIT | 2026-03-06 10:00 | 3183.004 |  | Repair | 35
110 | T-34024 | State Library of NSW - 1 Shakespeare Place, S | State Library of NSW | John Minai | PERFORMED | 2026-03-06 13:30 | 0 |  | Callout | 32
111 | T-33494 | Space 207 - 207 Pacific Highway, St Leonards, | Altis Bulky Retail ATF Altis | John Minai | REVISIT | 2026-03-09 06:00 | 1040 |  | Repair | 36
112 | T-34126 | By the Bay Investments - 2 Giffnock Avenue, N | ESSC, REM Colliers Internati | Gordon Jenkins | PERFORMED | 2026-03-09 09:04 | 460 |  | Callout | 29
113 | T-34151 | 40 Ricketty Road, Mascot, NSW 2020 | Henderson & Horning Pty Ltd | John Minai | REVISIT | 2026-03-10 06:00 | 460 |  | Callout | 29
114 | T-32692 | Precinct 5 AU186 - 3 Tundra Close, Kemps Kree | Goodman Property Services (A |  | SCHEDULED | 2026-03-11 12:00 | 660.513 |  | Repair | 40
115 | T-34400 | Gateway Business Park - Unit 3/9/10 - 63-79 P | Cambooya Properties C/o Knig | Gordon Jenkins | PERFORMED | 2026-03-11 13:00 | 460 |  | Callout | 28
116 | T-32615 | PFM Corp (BLDG 2) - 147-151 Newton Road, Weth | Kenneth R Moras Property Hol | John Minai | REVISIT | 2026-03-12 06:00 | 1040.004 | ⚠ OVERLAP | Repair | 41
117 | T-34124 | 11-13 Orion Road, Lane Cove West, NSW 2066 | The Trustee for Gemstone Lan | John Minai | PERFORMED | 2026-03-12 08:45 | 0 | ⚠ OVERLAP | Callout | 29
118 | T-34621 | Blacktown City Council - 81-85 Flushcombe Roa | Stanton Hillier Parker | Gordon Jenkins | REVISIT | 2026-03-12 13:00 | 460 |  | Callout | 26
119 | T-34662 | (AU642) 70 Euston Road, Alexandria | FlameSafe Warranty (Contract | Jimmy Kak | PERFORMED | 2026-03-13 07:00 | 130 |  | Callout | 26
120 | T-11638 | Bronson & Jacobs - 70 Marple Avenue, Villawoo | George Vasili & Nick Vasili |  | SCHEDULED | 2026-03-16 06:00 | 7105.15 |  | Repair | 326
121 | T-34783 | 71 Owen Street, Glendenning, NSW 2761 | Lendlease Real Estate Invest | John Minai | PERFORMED | 2026-03-16 09:45 | 460 |  | Callout | 25
122 | T-35245 | Goodman AU543 - 33-38 Quarry Road (Bld B, Bld | Goodman Property Services (A | Hugo | REVISIT | 2026-03-16 16:00 | 580 |  | Callout | 22
123 | T-31974 | Club Ashfield - 1-11 Charlotte Street, Ashfie | Ashfield Catholic & Communit | John Minai | REVISIT | 2026-03-18 06:00 | 2425.8222 |  | Repair | 48
124 | T-34751 | State Library of NSW - 1 Shakespeare Place, S | State Library of NSW |  | SCHEDULED | 2026-03-18 06:00 | 580 |  | Callout | 25
125 | T-32691 | Goodman AU645 - Campus Business Park - 350-37 | Goodman Property Services (A | Gordon Jenkins | PERFORMED | 2026-03-20 06:00 | 0 |  | Repair | 40
126 | T-25283 | Resolution X - 21B Richmond Road, Homebush We | Cranden Investments Pty Ltd | Nu Unasa | REVISIT | 2026-03-20 09:00 | 2640 |  | Repair | 120
127 | T-35477 | ACU - Building 532 - 8-20 Napier Street, Nort | Australian Catholic Universi |  | SCHEDULED | 2026-03-20 13:00 | 460 |  | Callout | 20
128 | T-33543 | ACU - Building 533 - 33 Berry Street, North S | Knight Frank | Nu Unasa | INPROGRESS | 2026-03-21 08:00 | 1740 |  | Repair | 35
129 | T-35837 | Metrolink Corporate Park - 197-201 Coward Str | The Trust Company (Australia | Gordon Jenkins | REVISIT | 2026-03-23 07:00 | 6340 | ⚠ OVERLAP | Callout | 18
130 | T-35476 | Centuria - K&S Freighters - 1 Hope Street, St | Centuria Institutional Inves | Tim Hu | PERFORMED | 2026-03-23 11:00 | 469.9906 |  | Repair | 20
131 | T-32380 | POLYCELL - 20-22 Lidco Street, Arndell Park, | Polycell NSW Pty Ltd | Gordon Jenkins | PERFORMED | 2026-03-23 11:00 | 460 | ⚠ OVERLAP | Callout | 42
132 | T-35777 | Coles CFC - 154 Cowpasture Road, Wetherill Pa | The Trustee for Charter Hall | Darren Brailey | REVISIT | 2026-03-24 05:30 | 0 |  | Callout | 19
133 | T-35784 | Goodman AU877 - Silverwater D/C - Light & Won | Goodman Property Services (A | Gordon Jenkins | PERFORMED | 2026-03-24 06:00 | 460 | ⚠ OVERLAP | Callout | 19
134 | T-35114 | ACU - Building 600-650 - 25a Baker Road, Stra | Australian Catholic Universi | Gordon Jenkins | REVISIT | 2026-03-24 08:30 | 130 | ⚠ OVERLAP | Callout | 22
135 | T-36204 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ | Gordon Jenkins | REVISIT | 2026-03-25 07:30 | 520 | ⚠ OVERLAP | Repair | 13
136 | T-34395 | PPIF - 9 George Street, Parramatta, NSW 2150 | Talish Property Group C/- Kn |  | SCHEDULED | 2026-03-25 08:00 | 780.003 |  | Repair | 28
137 | T-32680 | 372-394 Elizabeth Street, Surry Hills, NSW 20 | Contec Properties Pty Ltd |  | SCHEDULED | 2026-03-25 10:15 | 460 |  | Callout | 40
138 | T-36205 | Centennial Park - Grand Drive Sydney NSW 2021 | Greater Sydney Parklands C/ | Gordon Jenkins | REVISIT | 2026-03-25 11:30 | 590 | ⚠ OVERLAP | Repair | 13
139 | T-34390 | Goodman AU240 - Park View Business Park - 3 T | Goodman Property Services (A | Gordon Jenkins | REVISIT | 2026-03-26 07:01 | 7392.3055 |  | Repair | 28
140 | T-35708 | NIMBE - 39-47 Regent Street, Chippendale, NSW | Intera Group |  | SCHEDULED | 2026-03-26 10:00 | 700.102 |  | Repair | 19
141 | T-33437 | State Library of NSW - 1 Shakespeare Place, S | State Library of NSW |  | SCHEDULED | 2026-03-27 06:00 | 330 |  | Callout | 36
142 | T-35710 | ACU - Building 526 - 8-10 Berry Street, North | Australian Catholic Universi |  | SCHEDULED | 2026-03-27 09:00 | 520.002 |  | Repair | 19
143 | T-36664 | Frutex - 20 St Albans Road, Kingsgrove, NSW 2 | Sterilisation Technologies A | Darren Brailey | PERFORMED | 2026-03-27 10:00 | 460 | ⚠ OVERLAP | Callout | 11
144 | T-36796 | Goodman AU059 Lidcombe Business Park (Buildin | Goodman Property Services (A | Darren Brailey | REVISIT | 2026-03-27 13:10 | 460 | ⚠ OVERLAP | Callout | 11
145 | T-36961 | Landhop Chatswood - 11 Spring Street, Chatswo | Landhop Pty Ltd | Hugo | INPROGRESS | 2026-03-27 16:00 | 580 |  | Callout | 11
146 | T-37163 | 1 YORK - 1 York Street, Sydney, NSW 2000 | York II Sub Trust | Hugo | INPROGRESS | 2026-03-30 17:30 | 0 |  | Callout | 8
147 | T-36637 | Ya Zhou Wen Hua Enterprises - 541-543 Kent St | C/- ED Realty | Gordon Jenkins | PERFORMED | 2026-03-31 07:00 | 460 | ⚠ OVERLAP | Callout | 11
148 | T-37226 | ASICS - 6 Darling Street, Marsden Park - NSW | Ganian Pty Ltd ATF Blacktown | Gordon Jenkins | PERFORMED | 2026-03-31 09:00 | 460 | ⚠ OVERLAP | Callout | 8
149 | T-37324 | Jacfin Ricoh - 4 Telopea Place, Eastern Cree | FlameSafe Warranty (Contract | Gordon Jenkins | PERFORMED | 2026-03-31 11:00 | 460 | ⚠ OVERLAP | Callout | 7
150 | T-37951 | Costco Wholesale - 17-21 Parramatta Road, Aub | Costco Wholesale Auburn | Darren Brailey | PERFORMED | 2026-04-01 05:30 | 460 | ⚠ OVERLAP | Callout | 6
151 | T-37161 | Linfox - 27-49 Lenore Drive, Erskine Park, NS | C/-JLL | Gordon Jenkins | PERFORMED | 2026-04-01 08:00 | 460 | ⚠ OVERLAP | Callout | 8
152 | T-37987 | Goodman AU210 - Gateway Industrial Estate - B | Goodman Property Services (A | Gordon Jenkins | PERFORMED | 2026-04-01 11:40 | 460 | ⚠ OVERLAP | Callout | 6
153 | T-36038 | 3M - 1A Rivett Road, North Ryde, NSW 2113 | Quality Green Metro Pty Ltd | Gordon Jenkins | PERFORMED | 2026-04-01 12:00 | 0 | ⚠ OVERLAP | Repair | 14
154 | T-38083 | Jacfin Ricoh - 4 Telopea Place, Eastern Cree | The Trustee for Smithfield I | Darren Brailey | PERFORMED | 2026-04-01 14:00 | 460 | ⚠ OVERLAP | Callout | 6
155 | T-36632 | 45 Britton St, Smithfield | CBIIP 45B Pty Ltd | Gordon Jenkins | PERFORMED | 2026-04-02 06:00 | 460 | ⚠ OVERLAP | Callout | 11
156 | T-36634 | 78 Templar Road, Erskine Park, NSW 2759 | LHD TC Pty Ltd ATF LHD Sub I | Gordon Jenkins | PERFORMED | 2026-04-02 07:00 | 460 | ⚠ OVERLAP | Callout | 11
157 | T-38183 | LOGOS - Building 4 - 145 Hollinsworth Road, M | Logos Property Management Pt | Gordon Jenkins | PERFORMED | 2026-04-02 10:00 | 0 | ⚠ OVERLAP | Callout | 5
158 | T-37325 | ACU - Building 600-650 - 25a Baker Road, Stra | Australian Catholic Universi | Gordon Jenkins | REVISIT | 2026-04-07 07:00 | 460 |  | Callout | 7
159 | T-34391 | Goodman AU240 - Park View Business Park - 3 T | Goodman Property Services (A | Darren Brailey | PERFORMED | 2026-04-07 12:00 | 0 |  | Repair | 28
160 | T-38182 | Kraft Heinz - 92-96 Station Road, Seven Hills | Kraft-Heinz Co Australia Ltd |  | SCHEDULED | 2026-04-07 12:00 | 460 |  | Repair | 5
161 | T-36829 | Gateway Business Park - Unit 3/9/10 - 63-79 P | Cambooya Properties C/o Knig |  | SCHEDULED | 2026-04-08 07:00 | 3190 |  | Repair | 11
162 | T-38842 | 15-19 McPherson St, Banksmeadow, NSW 2019 | Roth Industrial | Gordon Jenkins | REVISIT | 2026-04-09 07:00 | 1660 |  | Repair | -1
163 | T-36073 | 1 YORK - 1 York Street, Sydney, NSW 2000 | York II Sub Trust |  | SCHEDULED | 2026-04-10 06:00 | 460 |  | Callout | 14
164 | T-38249 | 223-225 Liverpool Street, Darlinghurst, NSW 2 | Forza Capital Pty Ltd ATF Fo | Gordon Jenkins | SCHEDULED | 2026-04-10 07:00 | 460 |  | Callout | 5
165 | T-33860 | City of Parramatta Council - 9 Wentworth Stre | C/- Colliers Int’l Pty Ltd | Nu Unasa | REVISIT | 2026-04-10 11:00 | 520.002 |  | Repair | 33
166 | T-39238 | Goodman AU106 - M5 Industry Park - Building 1 | Goodman Property Services (A |  | SCHEDULED | 2026-04-10 12:00 | 0 |  | Repair | -2
167 | T-37159 | Jacfin Ricoh - 4 Telopea Place, Eastern Cree | FlameSafe Warranty (Contract |  | SCHEDULED | 2026-04-13 06:00 | 1325.0025 |  | Repair | 8
168 | T-36078 | Silverwater Industrial Park - Corner Fariola | Lendlease Real Estate Invest | Gordon Jenkins | REVISIT | 2026-04-14 06:00 | 1040.004 |  | Repair | 14
169 | T-33531 | Mandarin Centre - 65 Albert Ave, Chatswood NS | Mandarin Developments Pty Lt |  | SCHEDULED | 2026-04-14 06:00 | 2865.004 |  | Repair | 35
170 | T-33490 | Costas - 4 Beach Street, Eastern Creek, NSW 2 | Lendlease Real Estate Invest | Gordon Jenkins | REVISIT | 2026-04-15 06:00 | 29772.4184 |  | Repair | 36
171 | T-32509 | 26 Nelson Road, Yennora, NSW 2161 | The Trust Company (Australia |  | SCHEDULED | 2026-04-23 06:00 | 3283.2348 |  | Repair | 42
172 | T-32610 | Goodman AU820 - City West Office Park - Build | Goodman Property Services (A |  | SCHEDULED | 2026-04-27 06:00 | 1670.762 |  | Repair | 41
173 | T-36636 | Metrolink Corporate Park - 197-201 Coward Str | The Trust Company (Australia |  | SCHEDULED | 2026-04-27 10:00 | 460 |  | Callout | 11
174 | T-34915 | 11-13 Orion Road, Lane Cove West, NSW 2066 | The Trustee for Gemstone Lan |  | SCHEDULED | 2026-04-28 06:00 | 1753.9506 |  | Repair | 25
175 | T-36072 | Space 207 - 207 Pacific Highway, St Leonards, | Altis Bulky Retail ATF Altis |  | SCHEDULED | 2026-04-29 06:00 | 5673.04 |  | Repair | 14
176 | T-36074 | Labour Council of NSW - 377-383 Sussex Street | Unions NSW Property and Serv |  | SCHEDULED | 2026-04-30 06:00 | 460 |  | Repair | 14
177 | T-36467 | Goodman AU059 Lidcombe Business Park (Buildin | Goodman Property Services (A |  | SCHEDULED | 2026-05-01 06:00 | 1733.413 |  | Repair | 12
178 | T-36631 | Freight Assist Australia - 26 Pavesi Street, | Cambooya Properties C/- Knig |  | SCHEDULED | 2026-05-04 06:00 | 650.0025 |  | Repair | 11
179 | T-36635 | COLES RRM - 54 Templar Road, Erskine Park, NS | Retail Ready Operations Aust |  | SCHEDULED | 2026-05-05 06:00 | 9587.818 |  | Repair | 11
180 | T-21783 | TRS - 170 Newton Road, Wetherill Park, NSW 21 | Newton Road Holdings Pty Ltd | Gordon Jenkins | SCHEDULED | 2026-09-25 06:00 | 7796 |  | Repair | 154
180 of 180 shown | [6 empty] | 431691.23

## TECHNICIAN KPI
FLAMESAFE FIRE — Technician Performance KPI Register · All 12 Technicians
08 April 2026 · Completion rate, value, and workload per technician
TECHNICIAN | TASKS ASSIGNED | TASKS PERFORMED | COMPLETION % | TOTAL VALUE ($) | AVG VALUE ($) | REPAIRS | CALLOUTS | REPAIR VALUE ($) | CALLOUT VALUE ($) | REVISIT COUNT | SCHEDULED | PRIORITY — CRITICAL | PRIORITY — HIGH | % OF TEAM VALUE
Gordon Jenkins | 59 | 18 | 30.51% | 185409.4637 | 3142.5333 | 38 | 21 | 170659.4637 | 14750 | 33 | 5 | 7 | 24 | 36.85%
Nu Unasa | 43 | 3 | 6.977% | 95413.8742 | 2218.9273 | 22 | 21 | 70691.8742 | 24722 | 35 | 3 | 4 | 32 | 18.96%
John Minai | 20 | 3 | 15% | 37655.8736 | 1882.7937 | 11 | 9 | 35235.8736 | 2420 | 15 | 1 | 1 | 14 | 7.483%
Bailey Arthur | 1 | 0 | 0% | 12263.736 | 12263.736 | 1 | 0 | 12263.736 | 0 | 1 | 0 | 1 | 0 | 2.437%
Darren Brailey | 9 | 5 | 55.56% | 7205.442 | 800.6047 | 3 | 6 | 4905.442 | 2300 | 3 | 1 | 0 | 1 | 1.432%
Ryan Robinson | 2 | 0 | 0% | 2988.0025 | 1494.0013 | 1 | 1 | 2528.0025 | 460 | 1 | 1 | 0 | 1 | 0.5938%
Nick Hollingsworth | 1 | 0 | 0% | 2388.008 | 2388.008 | 1 | 0 | 2388.008 | 0 | 1 | 0 | 0 | 1 | 0.4746%
Hugo | 5 | 0 | 0% | 2300.63 | 460.126 | 1 | 4 | 680.63 | 1620 | 1 | 0 | 0 | 0 | 0.4572%
Haider Al-Heyoury | 1 | 0 | 0% | 1600 | 1600 | 0 | 1 | 0 | 1600 | 1 | 0 | 0 | 1 | 0.318%
Tim Hu | 1 | 1 | 100% | 469.9906 | 469.9906 | 1 | 0 | 469.9906 | 0 | 0 | 0 | 0 | 0 | 0.0934%
Jimmy Kak | 1 | 1 | 100% | 130 | 130 | 0 | 1 | 0 | 130 | 0 | 0 | 0 | 0 | 0.02583%
TOTAL / AVERAGE | 143 | 31 | 0% | 347825.0206 | 0
TECHNICIAN VALUE COMPARISON · Total Task Value by Technician
Gordon | 185409.4637
Nu | 95413.8742
John | 37655.8736
Bailey | 12263.736
Darren | 7205.442
Ryan | 2988.0025
Nick | 2388.008
Hugo | 2300.63
Jade | 2217
Haider | 1600
Tim | 469.9906
Jimmy | 130

## CLIENT BREAKDOWN
FLAMESAFE FIRE — Client Revenue & Account Analysis
All clients ranked by total task value · 08 April 2026
CLIENT NAME | TASKS | TOTAL VALUE ($) | AVG VALUE ($) | REPAIRS | CALLOUTS | REPAIR VALUE ($) | CALLOUT VALUE ($) | % OF REVENUE | RANK
Lendlease Real Estate Investments Ltd C/- JLL | 6 | 42368.9154 | 7061.4859 | 3 | 3 | 40868.9154 | 1500 | 8.42% | 1
Goodman Property Services (Aust) Pty Limited SC01822 | 25 | 34014.4777 | 1360.5791 | 12 | 13 | 30214.4777 | 3800 | 6.76% | 2
The Trustee For Gemstone Arndell Park Asset | 2 | 20674.1535 | 10337.0768 | 2 | 0 | 20674.1535 | 0 | 4.109% | 3
Retail Ready Operations Australia | 3 | 19739.818 | 6579.9393 | 2 | 1 | 19279.818 | 460 | 3.923% | 4
Jones Lang LaSalle (NSW) Pty Ltd | 9 | 17737.8846 | 1970.8761 | 4 | 5 | 12377.8846 | 5360 | 3.525% | 5
Inner West Council C/- Knight Frank Australia Pty Ltd | 1 | 15682 | 15682 | 0 | 1 | 0 | 15682 | 3.116% | 6
Sterilisation Technologies Australia Pty Ltd | 3 | 14588.281 | 4862.7603 | 2 | 1 | 14128.281 | 460 | 2.899% | 7
Primary Connect | 1 | 14387.3845 | 14387.3845 | 1 | 0 | 14387.3845 | 0 | 2.859% | 8
Centuria Property Funds No. 2 Ltd ACF ACN 062 671 872 Pty Ltd ATF BIPT Marple Ave Sub Trust Level 41, Chifley Tower 2 Chifley Square SYDNEY NSW 2000 | 1 | 13702.25 | 13702.25 | 1 | 0 | 13702.25 | 0 | 2.723% | 9
Centuria Institutional Investment No. 3 Pty Ltd ATF BIPT Preston No. 1 Sub Trust | 1 | 13457.86 | 13457.86 | 1 | 0 | 13457.86 | 0 | 2.674% | 10
Impact International | 1 | 12263.736 | 12263.736 | 1 | 0 | 12263.736 | 0 | 2.437% | 11
The Trust Company (Australia) Ltd ATF Ascendas Business Park Trust No.1 C/- Colliers | 5 | 12175.008 | 2435.0016 | 1 | 4 | 2895.008 | 9280 | 2.42% | 12
Australian Catholic Universities (ACU) | 8 | 11855.9263 | 1481.9908 | 4 | 4 | 10345.9263 | 1510 | 2.356% | 13
C/- Steven Krulis Real Estate Consultants | 1 | 11120.0209 | 11120.0209 | 1 | 0 | 11120.0209 | 0 | 2.21% | 14
Kraft-Heinz Co Australia Ltd | 2 | 10944 | 5472 | 2 | 0 | 10944 | 0 | 2.175% | 15
C/- TGC | 2 | 10504.3445 | 5252.1722 | 2 | 0 | 10504.3445 | 0 | 2.087% | 16
Logos Property Management Pty Limited | 5 | 9880.002 | 1976.0004 | 2 | 3 | 3520.002 | 6360 | 1.963% | 17
Newton Road Holdings Pty Ltd | 1 | 7796 | 7796 | 1 | 0 | 7796 | 0 | 1.549% | 18
Linfox Australia | 3 | 7668.005 | 2556.0017 | 3 | 0 | 7668.005 | 0 | 1.524% | 19
Pengton No. 1 Pty Ltd ATF Pengton No. 1 Unit Trust | 1 | 7507.5684 | 7507.5684 | 1 | 0 | 7507.5684 | 0 | 1.492% | 20
TCAL ATF Altis Bulky Sub Trust 3 Erskine Park C/- Knight Frank Australia Pty Ltd | 2 | 7295.8271 | 3647.9136 | 2 | 0 | 7295.8271 | 0 | 1.45% | 21
George Vasili & Nick Vasili C/- CBRE | 1 | 7105.15 | 7105.15 | 1 | 0 | 7105.15 | 0 | 1.412% | 22
X Commercial | 1 | 7065.508 | 7065.508 | 1 | 0 | 7065.508 | 0 | 1.404% | 23
Paspaley Pearls Properties Pty Ltd | 3 | 6865.008 | 2288.336 | 3 | 0 | 6865.008 | 0 | 1.364% | 24
Altis Bulky Retail ATF Altis Bulky Sub Trust 4 The Trust Company (Australia) LTD ACF Altis Bulky Sub Trust 4 | 2 | 6713.04 | 3356.52 | 2 | 0 | 6713.04 | 0 | 1.334% | 25
Lendlease Funds Management Ltd | 2 | 6530 | 3265 | 1 | 1 | 6400 | 130 | 1.298% | 26
Knight Frank | 3 | 6404.006 | 2134.6687 | 3 | 0 | 6404.006 | 0 | 1.273% | 27
Unions NSW Property and Services Limited | 3 | 6010 | 2003.3333 | 2 | 1 | 5550 | 460 | 1.194% | 28
Electus Distribution Pty Ltd | 1 | 5383.0095 | 5383.0095 | 1 | 0 | 5383.0095 | 0 | 1.07% | 29
C/- MMJ Sydney Pty Ltd | 1 | 4947.5221 | 4947.5221 | 1 | 0 | 4947.5221 | 0 | 0.9832% | 30
State Library of NSW | 4 | 4816.208 | 1204.052 | 1 | 3 | 3906.208 | 910 | 0.9571% | 31
One Funds Management Limited ATF Ben Lee Property Trust No 5 | 1 | 4728.67 | 4728.67 | 1 | 0 | 4728.67 | 0 | 0.9397% | 32
C/- Colliers Int’l Pty Ltd | 4 | 4710.002 | 1177.5005 | 2 | 2 | 3790.002 | 920 | 0.936% | 33
C/- ED Realty | 2 | 4634.009 | 2317.0045 | 1 | 1 | 4174.009 | 460 | 0.9209% | 34
KNAPP & Associates | 1 | 4630.008 | 4630.008 | 1 | 0 | 4630.008 | 0 | 0.9201% | 35
The Kitchenary Pty Ltd | 2 | 4610.39 | 2305.195 | 1 | 1 | 4030.39 | 580 | 0.9162% | 36
117 York Street Pty Limited | 1 | 4568.813 | 4568.813 | 1 | 0 | 4568.813 | 0 | 0.9079% | 37
Vanessa Aus Sub TC Pty Ltd ATF Vanessa Aus Sub Trust C/- CBRE Pty Ltd NSW Rents Trust | 1 | 4195.004 | 4195.004 | 1 | 0 | 4195.004 | 0 | 0.8337% | 38
Clara & Matthew Pty Ltd | 1 | 3700.006 | 3700.006 | 1 | 0 | 3700.006 | 0 | 0.7353% | 39
Cambooya Properties C/o Knight Frank Australia Pty Ltd | 2 | 3650 | 1825 | 1 | 1 | 3190 | 460 | 0.7254% | 40
Strata Plan 722 | 2 | 3354.435 | 1677.2175 | 2 | 0 | 3354.435 | 0 | 0.6666% | 41
Excel Building Management | 4 | 3317.63 | 829.4075 | 3 | 1 | 3317.63 | 0 | 0.6593% | 42
The Trust Company (Australia) Limited ATF FIP Hold 1 Trust | 1 | 3283.2348 | 3283.2348 | 1 | 0 | 3283.2348 | 0 | 0.6525% | 43
Ingleburn Industrial Property Co Pty Ltd | 1 | 3183.004 | 3183.004 | 1 | 0 | 3183.004 | 0 | 0.6325% | 44
Greater Sydney Parklands C/ - JLL | 6 | 3164 | 527.3333 | 6 | 0 | 3164 | 0 | 0.6288% | 45
Uturn Reuse Pty Limited | 1 | 3133.2258 | 3133.2258 | 1 | 0 | 3133.2258 | 0 | 0.6227% | 46
Mandarin Developments Pty Ltd C-/ Colliers International (NSW) Pty Ltd | 1 | 2865.004 | 2865.004 | 1 | 0 | 2865.004 | 0 | 0.5694% | 47
AM Property Plus C/- IOOF Investment Services Ltd C-/ Colliers | 1 | 2780.003 | 2780.003 | 1 | 0 | 2780.003 | 0 | 0.5525% | 48
Cranden Investments Pty Ltd | 1 | 2640 | 2640 | 1 | 0 | 2640 | 0 | 0.5246% | 49
Forza Capital Pty Ltd ATF Forza 223 Liverpool Fund | 1 | 2628.002 | 2628.002 | 1 | 0 | 2628.002 | 0 | 0.5223% | 50
Ashfield Catholic & Community Club Ltd | 1 | 2425.8222 | 2425.8222 | 1 | 0 | 2425.8222 | 0 | 0.4821% | 51
Vassk Investments Pty Ltd ATF Greenhills Estate Unit Trust C/-CBRE | 1 | 2388.008 | 2388.008 | 1 | 0 | 2388.008 | 0 | 0.4746% | 52
PDC Tech Pty Ltd | 1 | 2380.003 | 2380.003 | 1 | 0 | 2380.003 | 0 | 0.473% | 53
CSOF Sub Trust No. 2 ABN 52 847 795 285 | 1 | 2360 | 2360 | 1 | 0 | 2360 | 0 | 0.469% | 54
N G P Investments (no 2) Pty Ltd C/o Mercer Property Pty Ltd | 1 | 2351.01 | 2351.01 | 1 | 0 | 2351.01 | 0 | 0.4672% | 55
StorHub Australia | 1 | 2335.608 | 2335.608 | 1 | 0 | 2335.608 | 0 | 0.4641% | 56
FlameSafe Fire Protection (Testing Purposes) | 1 | 2217 | 2217 | 0 | 1 | 0 | 2217 | 0.4406% | 57
The Trustee for Gemstone Lane Cove Asset | 3 | 2213.9506 | 737.9835 | 1 | 2 | 1753.9506 | 460 | 0.44% | 58
CBIIP 17S Pty Ltd | 1 | 2098.7851 | 2098.7851 | 1 | 0 | 2098.7851 | 0 | 0.4171% | 59
West Infill Sub TC PTY LTD ATF West Infill Sub II Trust C/- CBRE Pty Ltd | 1 | 2069.927 | 2069.927 | 1 | 0 | 2069.927 | 0 | 0.4114% | 60
Shead Real Estate Pty Ltd | 1 | 1985 | 1985 | 1 | 0 | 1985 | 0 | 0.3945% | 61
Grand Hill Pty Ltd | 1 | 1970 | 1970 | 1 | 0 | 1970 | 0 | 0.3915% | 62
FlameSafe Warranty (Contracts) | 3 | 1915.0025 | 638.3342 | 1 | 2 | 1325.0025 | 590 | 0.3806% | 63
Goodman Fielder Consumer Foods Pty Ltd | 1 | 1893.003 | 1893.003 | 1 | 0 | 1893.003 | 0 | 0.3762% | 64
Aliro Trusco 1 Pty Ltd ATF the 159-163 Newton Road Trust C/- Colliers | 1 | 1630 | 1630 | 1 | 0 | 1630 | 0 | 0.3239% | 65
Andrews Meat Industries Pty Ltd | 1 | 1560 | 1560 | 1 | 0 | 1560 | 0 | 0.31% | 66
Yao Kai Pty Ltd | 1 | 1195.282 | 1195.282 | 1 | 0 | 1195.282 | 0 | 0.2375% | 67
Barwon Investment Partners Pty Ltd ACN 116 012 009 as trustee of the Barwon Institutional Healthcare Property Fund ABN 20 296 879 068 | 1 | 1067.006 | 1067.006 | 1 | 0 | 1067.006 | 0 | 0.212% | 68
Goodman Property Services (Aust) Pty Limited SC01822 | 1 | 1040.004 | 1040.004 | 1 | 0 | 1040.004 | 0 | 0.2067% | 69
Kenneth R Moras Property Holdings Pty Ltd | 1 | 1040.004 | 1040.004 | 1 | 0 | 1040.004 | 0 | 0.2067% | 70
Sydney Trains | 2 | 1040 | 520 | 0 | 2 | 0 | 1040 | 0.2067% | 71
Henderson & Horning Pty Ltd | 2 | 920 | 460 | 0 | 2 | 0 | 920 | 0.1828% | 72
Royal Life Saving NSW | 1 | 920 | 920 | 0 | 1 | 0 | 920 | 0.1828% | 73
Talish Property Group C/- Knight Frank Australia Pty Ltd | 1 | 780.003 | 780.003 | 1 | 0 | 780.003 | 0 | 0.155% | 74
LSH Auto (Sydney) Pty Ltd | 1 | 734.001 | 734.001 | 1 | 0 | 734.001 | 0 | 0.1459% | 75
Intera Group | 1 | 700.102 | 700.102 | 1 | 0 | 700.102 | 0 | 0.1391% | 76
Nks (NSW) Pty Ltd C/- Dunnet Properties Pty Ltd Pty Ltd | 1 | 680.63 | 680.63 | 1 | 0 | 680.63 | 0 | 0.1353% | 77
7 Box Sub TC Pty Ltd ATF 7 Box Sub Trust | 1 | 650.0025 | 650.0025 | 1 | 0 | 650.0025 | 0 | 0.1292% | 78
Cambooya Properties C/- Knight Frank Australia Pty Ltd | 1 | 650.0025 | 650.0025 | 1 | 0 | 650.0025 | 0 | 0.1292% | 79
The Trust Company Limited in its capacity as agent for CHPine ATF Minto Trust Bieson P/ L ATF the CHPIP Minto Trust | 1 | 590 | 590 | 1 | 0 | 590 | 0 | 0.1172% | 80
Landhop Pty Ltd | 1 | 580 | 580 | 0 | 1 | 0 | 580 | 0.1153% | 81
Centuria Institutional Investment No. 3 Pty Ltd ATF AIR Enfield Trust | 1 | 469.9906 | 469.9906 | 1 | 0 | 469.9906 | 0 | 0.0934% | 82
ESSC, REM Colliers International | 2 | 460 | 230 | 0 | 2 | 0 | 460 | 0.09141% | 83
Polycell NSW Pty Ltd | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 84
C/-JLL | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 85
CBIIP 45B Pty Ltd | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 86
Contec Properties Pty Ltd | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 87
Forza Capital Pty Ltd ATF Forza Liverpool Street Fund C/- CBRE Pty Ltd NSW Rents Trust | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 88
Asia Property AU 1 ATF the Concerto Camellia Property Trust | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 89
Costco Wholesale Auburn | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 90
Emirates | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 91
Ganian Pty Ltd ATF Blacktown Waste & Quarrying Land Unit Trust | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 92
Veolia Water Operations Pty Ltd | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 93
The Trustee for Charter Hall Prime Industrial Fund C/- CBRE Pty Ltd CBRE | 2 | 460 | 230 | 0 | 2 | 0 | 460 | 0.09141% | 94
Stanton Hillier Parker | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 95
Radio 2GB Sydney Pty Ltd | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 96
The Trustee for Smithfield Industrial Property Trust | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 97
Serbale Pty Limited | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 98
LHD TC Pty Ltd ATF LHD Sub I Trust | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 99
RAM Australia Elseie Street Buewood Trust | 1 | 460 | 460 | 0 | 1 | 0 | 460 | 0.09141% | 100
York II Sub Trust | 2 | 460 | 230 | 0 | 2 | 0 | 460 | 0.09141% | 101
DS Holdings and de Luxe Nominees C/O | 1 | 342.0024 | 342.0024 | 1 | 0 | 342.0024 | 0 | 0.06797% | 102
Arbor Property | 1 | 292 | 292 | 1 | 0 | 292 | 0 | 0.05803% | 103
Charter Hall Holdings Pty Ltd | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0% | 104
C/- Commercial Portfolio Management Pty Ltd | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0% | 105
Healthcare Logistics | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 106
Quality Green Metro Pty Ltd as Trustee for Quality Green Metro Unity Trust | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 107
Roth Industrial | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 108
TOTAL | 205 | 503202.5045 | 2726.471
TOP 10 CLIENT REVENUE CHART
Lendlease Real Estate Investme | 42368.9154
Goodman Property Services (Aus | 34014.4777
The Trustee For Gemstone Arnde | 20674.1535
Retail Ready Operations Austra | 19739.818
Jones Lang LaSalle (NSW) Pty L | 17737.8846
Inner West Council C/- Knight | 15682
Sterilisation Technologies Aus | 14588.281
Primary Connect | 14387.3845
Centuria Property Funds No. 2 | 13702.25
Centuria Institutional Investm | 13457.86